## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Manteswar | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. | SM/13280 | New | Material Requisition To Resource Division |  |  | RTOR000090/2022-2023 | 1243/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 10.3 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Manteswar | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. | SM/13280 | New | Material Requisition To Resource Division |  |  | RTOR000101/2022-2023 | 1632/BWD | 06/04/2023 | 06/04/2023 | Resource Division | 11.55 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Manteswar | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. | SM/13280 | New | Material Requisition To Resource Division |  |  | RTOR000618/2023-2024 | 4885/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 33.21 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Manteswar | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. | SM/13280 | New | New service connection charges for Sutra PWSS TW-1 |  |  | BILL/00792/2023-2024 | BP-2023-24-80 | 25/07/2023 | 25/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.89 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Manteswar | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. | SM/13280 | New | New service connection charges for Sutra PWSS TW-2 |  |  | BILL/00793/2023-2024 | BP-2023-24-81 | 25/07/2023 | 25/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.84 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Manteswar | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. | SM/13280 | New | SUTRA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Monteswar Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000743/2022-2023 | 1166/BWD | 14/03/2023 | 13/03/2024 | B.B.C. ENTERPRISE | 404.06 | 0 | 0 | 70
7 | PURBA BARDHAMAN | Manteswar | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. | SM/13280 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sutra Water Supply Scheme [ Block- Monteswar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000185/2023-2024 | 2967/CMD | 17/07/2023 | 16/08/2023 | M.S. ENTERPRISE | 27.67 | 0 | 0 | 100
8 | PURBA BARDHAMAN | Manteswar | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. | SM/13280 | New | Laying of additional pipeline and providing FHTC at SUTRA water supply scheme under Kalna Sub-Division, Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000157/2024-2025 | 2175/BWD | 12/06/2024 | 10/10/2024 | DUBE ENTERPRISE | 42.09 | 0 | 0 | 40
9 | PURBA BARDHAMAN | Manteswar | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. | SM/13280 | New | SUPPLY & INSTALLATION WORKS FOR SUTRA PWSS |  |  | BILL/02623/2023-2024 | BP-2023-24-558 | 21/02/2024 | 21/02/2024 | M.S. ENTERPRISE | 21.99 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Manteswar | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. | SM/13280 | New | Balance work for laying of pipeline, providing FHTC & other allied works in connection with Augmentation of MONTESWAR PWSS & SUTRA PWSS (SM/13280) under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000980/2024-2025 | 3572/BWD | 27/09/2024 | 27/03/2025 | BAKSHI ENTERPRISE | 51.14 | 0 | 0 | 30
11 | PURBA BARDHAMAN | Manteswar | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. | SM/13280 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 31/10/2025 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
Total | [13 empty] | 686.81 | 0 | 0