## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina-II | Burdwan Division | CHAK CHANDAN PIPED WATER SUPPLY SCHEME | SM/13281 | New | Material Requisition To Resource Division |  |  | RTOR000267/2023-2024 | 1898/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 11.69 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Raina-II | Burdwan Division | CHAK CHANDAN PIPED WATER SUPPLY SCHEME | SM/13281 | New | Material Requisition To Resource Division |  |  | RTOR000504/2023-2024 | 4028/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 8.29 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina-II | Burdwan Division | CHAK CHANDAN PIPED WATER SUPPLY SCHEME | SM/13281 | New | Material Requisition To Resource Division |  |  | RTOR000660/2023-2024 | 5118/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina-II | Central Mechanical | CHAK CHANDAN PIPED WATER SUPPLY SCHEME | SM/13281 | New | New service connection charges for Chak Chandan PWSS TW-1 |  |  | BILL/01667/2023-2024 | BP-2023-24-220 | 10/11/2023 | 10/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.07 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina-II | Central Mechanical | CHAK CHANDAN PIPED WATER SUPPLY SCHEME | SM/13281 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 23/12/2024 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina-II | Central Mechanical | CHAK CHANDAN PIPED WATER SUPPLY SCHEME | SM/13281 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chak Chandan Water Supply Scheme [ Block- Raina-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000726/2023-2024 | 4037/CMD | 29/08/2023 | 28/09/2023 | M/S. S.R. ENTERPRISE | 28.98 | 22.75 | 78.49 | 96
7 | PURBA BARDHAMAN | Raina-II | Central Mechanical | CHAK CHANDAN PIPED WATER SUPPLY SCHEME | SM/13281 | New | Emergency installation (for urgent FHTC) at Chak Chandan Water Supply Scheme PH 1 (part-3) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001675/2023-2024 | 82/CMSD | 15/01/2024 | 27/01/2024 | CHOUDHURY ENTERPRISE | 0.88 | 0.88 | 100 | 100
8 | PURBA BARDHAMAN | Raina-II | Central Mechanical | CHAK CHANDAN PIPED WATER SUPPLY SCHEME | SM/13281 | New | New electric connection for Chakchandan PWSS, PH-2. |  |  | BILL/01874/2023-2024 | BP-2023-24-340 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.49 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Raina-II | Burdwan Division | CHAK CHANDAN PIPED WATER SUPPLY SCHEME | SM/13281 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to UCHALAN, CHAK CHANDAN, SERPUR & KATNABIL Piped Water Supply Scheme under Raina II Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000367/2023-2024 | 3076/BWD | 18/07/2023 | 01/08/2027 | SK ALIM | 1307.56 | 216.37 | 16.55 | 75
10 | PURBA BARDHAMAN | Raina-II | Burdwan Division | CHAK CHANDAN PIPED WATER SUPPLY SCHEME | SM/13281 | New | Continuation Work Order for Supply of one No.Diesel Driven Ambassador Car No. WB:41H-4009 on hire basis for the office of the Assistant Engineer,Burdwan Sub-Division,PHE Dte(Period from 01-03-2025 to 31.05.2025) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001407/2024-2025 | 457/BSD | 28/02/2025 | 29/05/2025 | SK. ASFIA | 1.2 | 0 | 0 | 100
11 | PURBA BARDHAMAN | Raina-II | Central Mechanical | CHAK CHANDAN PIPED WATER SUPPLY SCHEME | SM/13281 | New | Supply and delivery of submersible pumping machinery (for urgent FHTC) for Chak Chandan Water Supply Scheme PH 1 (part-2) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001671/2023-2024 | 65/CMSD | 11/01/2024 | 23/01/2024 | CHOUDHURY ENTERPRISE | 0.86 | 0.86 | 100 | 100
12 | PURBA BARDHAMAN | Raina-II | Central Mechanical | CHAK CHANDAN PIPED WATER SUPPLY SCHEME | SM/13281 | New | Delivery of different Electro-mechanical items (for urgent FHTC) for Chak Chandan Water Supply Scheme PH 1 (part-1) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001669/2023-2024 | 08/CMSD | 02/01/2024 | 11/02/2024 | CHOUDHURY ENTERPRISE | 0.92 | 0.92 | 100 | 100
Total | [13 empty] | 1477.81 | 241.77 | 16.36