## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | HARIGRAM PIPED WATER SUPPLY SCHEME | SM/13292 | New | Material Requisition To Resource Division |  |  | RTOR000071/2022-2023 | 1252/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 7.5 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | HARIGRAM PIPED WATER SUPPLY SCHEME | SM/13292 | New | Material Requisition To Resource Division |  |  | RTOR000108/2022-2023 | 1643/BWD | 06/04/2023 | 06/04/2023 | Resource Division | 1.79 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | HARIGRAM PIPED WATER SUPPLY SCHEME | SM/13292 | New | Material Requisition To Resource Division |  |  | RTOR000717/2023-2024 | 5267/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 21.07 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | HARIGRAM PIPED WATER SUPPLY SCHEME | SM/13292 | New | New service connection charges for Harigram PWSS TW-2 |  |  | BILL/01707/2023-2024 | BP-2023-24-236 | 06/12/2023 | 06/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.69 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | HARIGRAM PIPED WATER SUPPLY SCHEME | SM/13292 | New | New service connection charges for Harigram PWSS TW-1 |  |  | BILL/01471/2023-2024 | BP-2023-24-169 | 27/09/2023 | 27/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.5 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | HARIGRAM PIPED WATER SUPPLY SCHEME | SM/13292 | New | Continuation order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte for the period of 01.12.2023 to 31.05.2024 | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001007/2023-2024 | 2751/BSD | 28/11/2023 | 29/05/2024 | SK.ASFIA | 2.4 | 0.4 | 16.65 | 70
7 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | HARIGRAM PIPED WATER SUPPLY SCHEME | SM/13292 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Harigram Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000590/2023-2024 | 3940/CMD | 23/08/2023 | 22/09/2023 | CHOUDHURY ENTERPRISE | 28.9 | 23.82 | 82.43 | 100
8 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | HARIGRAM PIPED WATER SUPPLY SCHEME | SM/13292 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 31/10/2024 | DILIP MAHATO | 53.14 | 0 | 0 | 12
9 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | HARIGRAM PIPED WATER SUPPLY SCHEME | SM/13292 | New | Supply and installation of Electro-Magnetic flow meter at HARIGRAM, KUCHUT & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000564/2024-2025 | 3103/CMD | 11/12/2024 | 09/02/2025 | S DUTTA | 15.06 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | HARIGRAM PIPED WATER SUPPLY SCHEME | SM/13292 | New | Allied works (OHR, FHTC, internal pathway, approach road and road restoration) for HARIGRAM PWSS under Bardhaman II Block within Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000722/2025-2026 | 1405/BWD | 16/05/2025 | 14/08/2025 | S.R. ENTERPRISE | 14.32 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | HARIGRAM PIPED WATER SUPPLY SCHEME | SM/13292 | New | HARIGRAM Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Burdwan-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000684/2022-2023 | 481/BWD | 08/02/2023 | 01/01/2025 | SAKTI ENTERPRISE | 262.46 | 236.52 | 90.12 | 81
Total | [13 empty] | 418.82 | 260.74 | 62.26