## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Baikunthapur Piped Water Supply Scheme | SM/13294 | New | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 4.39 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Baikunthapur Piped Water Supply Scheme | SM/13294 | New | Material Requisition To Resource Division |  |  | RTOR000218/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 1.97 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Baikunthapur Piped Water Supply Scheme | SM/13294 | New | Material Requisition To Resource Division |  |  | RTOR000707/2023-2024 | 5044/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Baikunthapur Piped Water Supply Scheme | SM/13294 | New | Hiring of inspection vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of the Assistant Engineer,under CMD PHE Dte. w.e.f -01/08/2024 to 30/09/2024 .[Under JJM Works] | ASSISTANT ENGINEER | Junior Engineer | ORD/000418/2024-2025 | 834/CMSD | 07/06/2024 | 07/08/2024 | PRODYUT GHOSH | 0.8 | 0.79 | 99.77 | 0
5 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Baikunthapur Piped Water Supply Scheme | SM/13294 | New | New service connection at BAIAKUNTHAPUR PWSS Ph-2 |  |  | BILL/02326/2023-2024 | BP-2023-24-443 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.73 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Baikunthapur Piped Water Supply Scheme | SM/13294 | New | New service connection at BAIAKUNTHAPUR PWSS Ph-1 |  |  | BILL/02325/2023-2024 | BP-2023-24-442 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.45 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Baikunthapur Piped Water Supply Scheme | SM/13294 | New | Shifting of pole for laying of water supply pipeline of Baikunthapur pwss under Burdwan Division, PHE Dte. [Ref ID-860315315, Application ID-100000120685, dt.-01/10/2024] |  |  | BILL/01091/2024-2025 | 1173/JJM | 17/12/2024 | 17/12/2024 | WBSEDCL | 0.89 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Baikunthapur Piped Water Supply Scheme | SM/13294 | New | New service connection charges for Baikunthapur PWSS TW-2 |  |  | BILL/02940/2023-2024 | BP-2023-24-517 | 08/02/2024 | 08/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.48 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Baikunthapur Piped Water Supply Scheme | SM/13294 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMRA & BAIKUNTHAPUR Piped Water Supply Scheme under Burdwan II Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000089/2023-2024 | 2214/BWD | 15/05/2023 | 31/08/2025 | CONCORD ENGINEERING | 750.87 | 213.55 | 28.44 | 55
10 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Baikunthapur Piped Water Supply Scheme | SM/13294 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Baikunthapur Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000663/2023-2024 | 4006/CMD | 29/08/2023 | 28/09/2023 | A.S. ENTERPRISE | 28.95 | 5.2 | 17.96 | 100
11 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Baikunthapur Piped Water Supply Scheme | SM/13294 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 31/10/2024 | DILIP MAHATO | 53.14 | 0 | 0 | 12
Total | [13 empty] | 873.12 | 219.55 | 25.14