## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Gangua Piped Water Supply Scheme | SM/13295 | New | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/08/2023 to 31/10/2023] |  |  | ORD/000845/2023-2024 | 1759/BSD | 28/07/2023 | 02/10/2023 | MD HASIN | 0.85 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Gangua Piped Water Supply Scheme | SM/13295 | New | Material Requisition To Resource Division |  |  | RTOR000257/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 11.5 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Gangua Piped Water Supply Scheme | SM/13295 | New | Material Requisition To Resource Division |  |  | RTOR000514/2023-2024 | 4038/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 0.41 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Gangua Piped Water Supply Scheme | SM/13295 | New | Material Requisition To Resource Division |  |  | RTOR000667/2023-2024 | 5088/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Gangua Piped Water Supply Scheme | SM/13295 | New | New service connection for Gangua PWSS TW 2 |  |  | BILL/02414/2023-2024 | BP-2023-24-512 | 08/02/2024 | 08/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.61 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Gangua Piped Water Supply Scheme | SM/13295 | New | New service connection for Gangua W/S scheme TW No-1 |  |  | BILL/02274/2023-2024 | BP-2023-24-409 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.34 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Gangua Piped Water Supply Scheme | SM/13295 | New | GANGUA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Burdwan-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000525/2023-2024 | 3616/BWD | 18/08/2023 | 01/04/2025 | SHIVAM UN-EMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 340.75 | 161.59 | 47.42 | 95
8 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Gangua Piped Water Supply Scheme | SM/13295 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 31/10/2024 | DILIP MAHATO | 53.14 | 0 | 0 | 12
Total | [13 empty] | 444.06 | 161.59 | 36.39