## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Amra Piped Water Supply Scheme | SM/13296 | New | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 2.95 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Amra Piped Water Supply Scheme | SM/13296 | New | Material Requisition To Resource Division |  |  | RTOR000701/2023-2024 | 5060/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Amra Piped Water Supply Scheme | SM/13296 | New | Continuation Work for the supply of one no. Diesel driven Motor Cab/Maxi Cab (Air Conditioner) on hire basis for the office of the Assistant Engineer, to be used by the Assistant Engineer, RWS Burdwan Sub-Divn., PHE. Dte. (Period from 01/05/2024 to 30/06/2024) |  | Contractual Junior Engineer,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000151/2024-2025 | 154/RWS | 29/04/2024 | 29/06/2024 | MD HASIN | 0.8 | 0.55 | 68.59 | 0
4 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Amra Piped Water Supply Scheme | SM/13296 | New | Material Requisition To Resource Division |  |  | RTOR000771/2023-2024 | 195/BWD | 10/01/2024 | 10/01/2024 | Resource Division | 5.52 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Amra Piped Water Supply Scheme | SM/13296 | New | New Service connection forAmra PWSS TW-2. |  |  | BILL/02336/2023-2024 | BP-2023-24-473 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 16.94 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Amra Piped Water Supply Scheme | SM/13296 | New | New Service connection for Amra PWSS TW-1. |  |  | BILL/02337/2023-2024 | BP-2023-24-472 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.51 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Amra Piped Water Supply Scheme | SM/13296 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 31/10/2024 | DILIP MAHATO | 53.14 | 0 | 0 | 12
8 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Amra Piped Water Supply Scheme | SM/13296 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Amra Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000672/2023-2024 | 4005/CMD | 29/08/2023 | 01/06/2025 | S.K. ENTERPRISE | 28.98 | 22.82 | 78.73 | 85
9 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Amra Piped Water Supply Scheme | SM/13296 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMRA & BAIKUNTHAPUR Piped Water Supply Scheme under Burdwan II Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000089/2023-2024 | 2214/BWD | 15/05/2023 | 31/08/2025 | CONCORD ENGINEERING | 750.87 | 52.78 | 7.03 | 55
Total | [13 empty] | 888.16 | 76.15 | 8.57