## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | RUPSA PIPED WATER SUPPLY SCHEME | SM/13298 | New | Material Requisition To Resource Division |  |  | RTOR000079/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 8.1 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | RUPSA PIPED WATER SUPPLY SCHEME | SM/13298 | New | Material Requisition To Resource Division |  |  | RTOR000199/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 20.06 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | RUPSA PIPED WATER SUPPLY SCHEME | SM/13298 | New | Material Requisition To Resource Division |  |  | RTOR000731/2023-2024 | 5238/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 21.07 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | RUPSA PIPED WATER SUPPLY SCHEME | SM/13298 | New | Continuation order for Supply of 01(one) No. Diesel Driven Motor Cab (Bharat Stage-II) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Division (Burdwan North) P.H.E. Dte. Govt. of West Bengal (for the period of 01/01/2024 to 31/05/2024) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001180/2023-2024 | 995/DSD | 29/12/2023 | 29/06/2024 | SUJAUDDIN SEKH | 2 | 0.4 | 20 | 60
5 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | RUPSA PIPED WATER SUPPLY SCHEME | SM/13298 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 31/10/2024 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | RUPSA PIPED WATER SUPPLY SCHEME | SM/13298 | New | New service connection for Rupsa W/S scheme TW No-1 |  |  | BILL/02275/2023-2024 | BP-2023-24-410 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.27 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | RUPSA PIPED WATER SUPPLY SCHEME | SM/13298 | New | Quotation for new service connection at RUPSA PWSS PH-2 |  |  | BILL/00384/2024-2025 | BP-2024-25-201 | 18/07/2024 | 18/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | RUPSA PIPED WATER SUPPLY SCHEME | SM/13298 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMRA, BALABATI, UKHRID & RUPSA Piped Water Supply Scheme under KHANDAGHOSH Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte.,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000008/2023-2024 | 1726/BWD | 13/04/2023 | 01/10/2025 | S.P. CONSTRUCTION | 1710.27 | 230.92 | 13.5 | 45
9 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | RUPSA PIPED WATER SUPPLY SCHEME | SM/13298 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Rupsa Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000706/2023-2024 | 4013/CMD | 29/08/2023 | 28/09/2023 | SAIKAT ENTERPRISE | 28.98 | 11.24 | 38.77 | 85
10 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | RUPSA PIPED WATER SUPPLY SCHEME | SM/13298 | New | Balance work for providing Functional Household Tap Connection (FHTC) within the command area BALABATI, AMRA & RUPSA W/S. Scheme of Khandaghosh Block under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001189/2024-2025 | 609/BWD | 11/02/2025 | 11/06/2025 | M/S S.S. ENTERPRISE | 194.58 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | RUPSA PIPED WATER SUPPLY SCHEME | SM/13298 | New | FIXING OF DISPLAY BOARD WITH M.S STRUCTURE CONTAINING LAND DESCRIPTION AT RUPSA PWSS AND OTHER SCHEMES (49 Nos.) WITHIN KHANDOGHOSH BLOCK UNDER BURDWAN DIVISION , PHE Dte. |  | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000947/2024-2025 | 1086/DSD | 11/12/2024 | 26/12/2024 | SOUMYAVASH DAS | 3.18 | 0 | 0 | 100
12 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | RUPSA PIPED WATER SUPPLY SCHEME | SM/13298 | New | Continuation for Operation of Distribution System , Rising main, Sluice Valves, including operation of sluice valves of RUPSA PWSS within Durgapur Sub-Division under Burdwan Division, PHE Dte. [Period for 01.10.2025 to 31.12.2025]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000791/2025-2026 | 1269/DSD | 25/09/2025 | 03/01/2026 | SHUBHRA KANTI GHOSH | 0.63 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | RUPSA PIPED WATER SUPPLY SCHEME | SM/13298 | New | Continuation for Operation of Distribution System , Rising main, Sluice Valves, including operation of sluice valves of RUPSA PWSS within Durgapur Sub-Division under Burdwan Division, PHE Dte. [Period for 01/01/2026 to 31/03/2026]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001102/2025-2026 | 1460/DSD | 30/12/2025 | 30/03/2026 | SHUBHRA KANTI GHOSH | 0.63 | 0 | 0 | 0
14 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | RUPSA PIPED WATER SUPPLY SCHEME | SM/13298 | New | Continuation for Operation of Distribution System , Rising main, Sluice Valves, including operation of sluice valves of RUPSA PWSS within Durgapur Sub-Division under Burdwan Division, PHE Dte. [Period for 01/04/2026 to 30/06/2026]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001145/2025-2026 | 222/DSD | 27/03/2026 | 26/06/2026 | SHUBHRA KANTI GHOSH | 0.63 | 0 | 0 | 0
Total | [13 empty] | 2046.94 | 242.56 | 11.85