## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | HARIPUR PIPED WATER SUPPLY SCHEME | SM/13315 | New | Material Requisition To Resource Division |  |  | RTOR000152/2023-2024 | 2155/BWD | 10/05/2023 |  | Resource Division | 10.75 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | HARIPUR PIPED WATER SUPPLY SCHEME | SM/13315 | New | New service connection charges for Haripur PWSS TW-1 |  |  | BILL/00820/2023-2024 | BP-2023-24-97 | 02/08/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.02 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | HARIPUR PIPED WATER SUPPLY SCHEME | SM/13315 | New | Material Requisition To Resource Division |  |  | RTOR000521/2023-2024 | 4284/BWD | 29/09/2023 |  | Resource Division | 0.55 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | HARIPUR PIPED WATER SUPPLY SCHEME | SM/13315 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at HARIPUR Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000164/2023-2024 | 2931/CMD | 12/07/2023 | 11/08/2023 | ASHIM UDYOG | 20.77 | 9.37 | 45.12 | 30
5 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | HARIPUR PIPED WATER SUPPLY SCHEME | SM/13315 | New | Material Requisition To Resource Division |  |  | RTOR000599/2023-2024 | 4905/BWD | 10/11/2023 |  | Resource Division | 4.86 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | HARIPUR PIPED WATER SUPPLY SCHEME | SM/13315 | New | HARIPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali I Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000774/2022-2023 | 1340/BWD | 22/03/2023 | 20/06/2023 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 94.46 | 57.64 | 61.02 | 55
7 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | HARIPUR PIPED WATER SUPPLY SCHEME | SM/13315 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000072/2024-2025 | 2397/CMD | 02/08/2024 | 31/10/2024 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | HARIPUR PIPED WATER SUPPLY SCHEME | SM/13315 | New | Different Types of work involved in connection with Augmentation of NAOPARA (SM/09407) & HARIPUR (SM/13315) water supply scheme Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000164/2024-2025 | 2203/BWD | 13/06/2024 | 11/10/2024 | MONDAL & CO. | 223.65 | 64.32 | 28.76 | 50
9 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | HARIPUR PIPED WATER SUPPLY SCHEME | SM/13315 | New | Withdrawing of pump motor set due to low discharge and installation of new pump motor set at Haripur PH 1 (Purbasthali-1 Block) water supply scheme under CMD P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001893/2023-2024 | 364/CMSD | 28/02/2024 | 14/03/2024 | ASHIM UDYOG | 0.67 | 0 | 0 | 0
Total | [13 empty] | 407.34 | 131.33 | 32.24