## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | HARIPUR PIPED WATER SUPPLY SCHEME | SM/13315 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at HARIPUR Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000164/2023-2024 | 2931/CMD | 12/07/2023 | 11/08/2023 | ASHIM UDYOG | 20.77 | 0 | 0 | 30
2 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | HARIPUR PIPED WATER SUPPLY SCHEME | SM/13315 | New | Material Requisition To Resource Division |  |  | RTOR000521/2023-2024 | 4284/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 0.55 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | HARIPUR PIPED WATER SUPPLY SCHEME | SM/13315 | New | Material Requisition To Resource Division |  |  | RTOR000152/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 10.75 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | HARIPUR PIPED WATER SUPPLY SCHEME | SM/13315 | New | Material Requisition To Resource Division |  |  | RTOR000599/2023-2024 | 4905/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 4.86 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | HARIPUR PIPED WATER SUPPLY SCHEME | SM/13315 | New | New service connection charges for Haripur PWSS TW-1 |  |  | BILL/00820/2023-2024 | BP-2023-24-97 | 02/08/2023 | 02/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.02 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | HARIPUR PIPED WATER SUPPLY SCHEME | SM/13315 | New | Supply and Delivery of standby pump motor set for Sipta, Uchitpur, Haripur & others Water Supply Scheme under CMD, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000142/2024-2025 | 2596/CMD | 27/08/2024 | 26/09/2024 | JOYGURU ENTERPRISE | 4.72 | 0 | 0 | 100
7 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | HARIPUR PIPED WATER SUPPLY SCHEME | SM/13315 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000072/2024-2025 | 2397/CMD | 02/08/2024 | 31/10/2024 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 0 | 30
8 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | HARIPUR PIPED WATER SUPPLY SCHEME | SM/13315 | New | HARIPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali I Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000774/2022-2023 | 1340/BWD | 22/03/2023 | 29/03/2024 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 94.46 | 0 | 0 | 100
Total | [13 empty] | 187.73 | 0 | 0