## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Material Requisition To Resource Division |  |  | RTOR000157/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 13.55 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Material Requisition To Resource Division |  |  | RTOR000472/2023-2024 | 3996/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 1.64 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | New service connection charges for Masgaria PWSS TW-1 |  |  | BILL/01428/2023-2024 | BP-2023-24-132 | 05/09/2023 | 05/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.75 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | New service connection charges for Masgaria PWSS TW-2 |  |  | BILL/01467/2023-2024 | BP-2023-24-165 | 26/09/2023 | 26/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.2 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KONRAPUR & MASGARIA Piped Water Supply Scheme under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000026/2023-2024 | 1765/BWD | 17/04/2023 | 16/04/2024 | M/S ASHA CONSTRUCTION | 710.72 | 202.16 | 28.44 | 43
6 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Supply and delivery of different Electro-mechanical items (for urgent FHTC) for masgaria Water Supply Scheme PH 2 (part-1) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001668/2023-2024 | 07/CMSD | 02/01/2024 | 12/01/2024 | DIPALI CONSTRUCTION | 0.92 | 0.92 | 100 | 100
7 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Emergency installation (for urgent FHTC) at Masgaria Water Supply Scheme PH 2 (part-3) under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001677/2023-2024 | 84/CMSD | 15/01/2024 | 27/01/2024 | DIPALI CONSTRUCTION | 0.8 | 0.8 | 100 | 100
8 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR MASGARIA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001145/2023-2024 | 1981/KSD | 09/02/2024 | 19/02/2024 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.33 | 0.33 | 99.78 | 2
9 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Supply and delivery of submersible pumping machinery (for urgent FHTC) for masgaria Water Supply Scheme PH 2 (part-2) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001673/2023-2024 | 67/CMSD | 11/01/2024 | 23/01/2024 | DIPALI CONSTRUCTION | 0.85 | 0.85 | 100 | 100
10 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Material Requisition To Resource Division |  |  | RTOR000803/2023-2024 | 294/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 14.63 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Addl quotation for New service connection charges for Masgaria PWSS TW-1 |  |  | BILL/01729/2023-2024 | BP-2023-24-240 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.44 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Different types of balance works involve in connection with KONRAPUR (SM/13419) & MASGORIA (SM/13318) Piped water supply scheme under Purbasthali-I Block within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001028/2024-2025 | 142/BWD | 08/01/2025 | 08/05/2025 | M/S ASHA CONSTRUCTION | 65.74 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000714/2024-2025 | 2979/CMD | 25/11/2024 | 23/02/2025 | H.K. DAS & CO. | 53.27 | 0 | 0 | 0
14 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at MASGARIA Water Supply Scheme [Block-PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000357/2023-2024 | 3505/CMD | 31/07/2023 | 30/08/2023 | M/S. SWAPAN BANERJEE | 21.55 | 19.38 | 89.91 | 95
Total | [13 empty] | 894.38 | 224.44 | 25.1