## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Material Requisition To Resource Division |  |  | RTOR000157/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 13.55 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Material Requisition To Resource Division |  |  | RTOR000472/2023-2024 | 3996/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 1.64 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | New service connection charges for Masgaria PWSS TW-1 |  |  | BILL/01428/2023-2024 | BP-2023-24-132 | 05/09/2023 | 05/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.75 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | New service connection charges for Masgaria PWSS TW-2 |  |  | BILL/01467/2023-2024 | BP-2023-24-165 | 26/09/2023 | 26/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.2 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KONRAPUR & MASGARIA Piped Water Supply Scheme under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000026/2023-2024 | 1765/BWD | 17/04/2023 | 16/04/2024 | M/S ASHA CONSTRUCTION | 710.72 | 0 | 0 | 43
6 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Supply and delivery of different Electro-mechanical items (for urgent FHTC) for masgaria Water Supply Scheme PH 2 (part-1) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001668/2023-2024 | 07/CMSD | 02/01/2024 | 12/01/2024 | DIPALI CONSTRUCTION | 0.92 | 0 | 0 | 100
7 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Emergency installation (for urgent FHTC) at Masgaria Water Supply Scheme PH 2 (part-3) under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001677/2023-2024 | 84/CMSD | 15/01/2024 | 27/01/2024 | DIPALI CONSTRUCTION | 0.8 | 0 | 0 | 100
8 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR MASGARIA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001145/2023-2024 | 1981/KSD | 09/02/2024 | 19/02/2024 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.33 | 0 | 0 | 2
9 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Supply and delivery of submersible pumping machinery (for urgent FHTC) for masgaria Water Supply Scheme PH 2 (part-2) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001673/2023-2024 | 67/CMSD | 11/01/2024 | 23/01/2024 | DIPALI CONSTRUCTION | 0.85 | 0 | 0 | 100
10 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Material Requisition To Resource Division |  |  | RTOR000803/2023-2024 | 294/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 14.63 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Addl quotation for New service connection charges for Masgaria PWSS TW-1 |  |  | BILL/01729/2023-2024 | BP-2023-24-240 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.44 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Providing leftout FHTC at different places of Malatipur village in order to declare swajal gram under the command area of Masgaria Piped Water Supply Scheme within Kalna Sub Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000764/2024-2025 | 3759/BWD | 29/10/2024 | 28/11/2024 | IYASIN DAFADAR | 7.8 | 0 | 0 | 100
13 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Providing left out FHTC at different places of Rajipur, Kansaripur village in order to declare swajal gram under the command area of Masgoria Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000712/2024-2025 | 3718/BWD | 29/10/2024 | 20/01/2025 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 8.45 | 0 | 0 | 100
14 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Providing left out FHTC at different places of Bachpur village in order to declare swajal gram under the command area of Masgoria Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000713/2024-2025 | 3719/BWD | 29/10/2024 | 20/01/2025 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 7.57 | 0 | 0 | 80
15 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Different types of balance works involve in connection with KONRAPUR (SM/13419) & MASGORIA (SM/13318) Piped water supply scheme under Purbasthali-I Block within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001028/2024-2025 | 142/BWD | 08/01/2025 | 08/05/2025 | M/S ASHA CONSTRUCTION | 65.74 | 0 | 0 | 0
16 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000714/2024-2025 | 2979/CMD | 25/11/2024 | 23/02/2025 | H.K. DAS & CO. | 53.27 | 0 | 0 | 0
17 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME | SM/13318 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at MASGARIA Water Supply Scheme [Block-PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000357/2023-2024 | 3505/CMD | 31/07/2023 | 30/08/2023 | M/S. SWAPAN BANERJEE | 21.55 | 0 | 0 | 95
Total | [13 empty] | 918.2 | 0 | 0