## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Samanti Piped Water Supply Scheme | SM/13319 | New | Supply & delivery of different dia. MJ Coller for FHTC as well as smooth running of different W/S. Schemes under Burdwan Division, P.H.E. Dte. [i.e. (1) Magra PWSS, Memari-I Block, (2) Kuchut PWSS, Memari - II Block, (3) Khundkuri PWSS, Khandaghosh Block & (4) Samanti PWSS, Burdwan - II Block)] |  |  | ORD/000653/2023-2024 | 4076/BWD | 13/09/2023 | 03/10/2023 | SSPR VALVE MANUFACTURING PVT LTD. | 20.63 | 5 | 24.24 | 100
2 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Samanti Piped Water Supply Scheme | SM/13319 | New | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 10.45 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Samanti Piped Water Supply Scheme | SM/13319 | New | Material Requisition To Resource Division |  |  | RTOR000170/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 23.19 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Samanti Piped Water Supply Scheme | SM/13319 | New | Material Requisition To Resource Division |  |  | RTOR000732/2023-2024 | 5237/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 21.07 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Samanti Piped Water Supply Scheme | SM/13319 | New | New service connection charges for Samanti PWSS TW-1 |  |  | BILL/00886/2023-2024 | BP-2023-24-112 | 10/08/2023 | 10/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.1 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Samanti Piped Water Supply Scheme | SM/13319 | New | New service connection for Samanti W/S scheme TW No-2 |  |  | BILL/02273/2023-2024 | BP-2023-24-411 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.6 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Samanti Piped Water Supply Scheme | SM/13319 | New | Restoration of hard shouldering and flank damaged during laying of PHE pipeline at Samanti village road from 0.00 Kmp to 3.00 Kmp within Samanti PWSS. |  |  | BILL/00138/2024-2025 | 226/JJM | 14/05/2024 | 14/05/2024 | EXECUTIVE ENGINEER-I, BURDWAN DIVISION, P.W.D. | 5.08 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Samanti Piped Water Supply Scheme | SM/13319 | New | SAMANTI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under BARDHAMAN-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000802/2022-2023 | 1536/BWD | 29/03/2023 | 31/12/2025 | G.B. CONSTRUCTION & CO. | 504.69 | 304.41 | 60.32 | 36
9 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Samanti Piped Water Supply Scheme | SM/13319 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 31/10/2024 | DILIP MAHATO | 53.14 | 0 | 0 | 12
Total | [13 empty] | 648.94 | 309.41 | 47.68