## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | MANGANPUR PIPED WATER SUPPLY SCHEME | SM/13327 | New | Material Requisition To Resource Division |  |  | RTOR000339/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 11.02 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | MANGANPUR PIPED WATER SUPPLY SCHEME | SM/13327 | New | Material Requisition To Resource Division |  |  | RTOR000475/2023-2024 | 3999/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 3.31 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | MANGANPUR PIPED WATER SUPPLY SCHEME | SM/13327 | New | New service connection charges for Manganpur PWSS TW-1 |  |  | BILL/01670/2023-2024 | BP-2023-24-227 | 10/11/2023 | 10/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.63 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | MANGANPUR PIPED WATER SUPPLY SCHEME | SM/13327 | New | Supply and delivery of portable generator set for emergency internal installation work at Manganpur and other Water Supply Scheme under CMD., PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001419/2023-2024 | 153/CMSD | 22/01/2024 | 06/02/2024 | M/S, MONDAL ASSOCIATES. | 2.11 | 2.11 | 100 | 100
5 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | MANGANPUR PIPED WATER SUPPLY SCHEME | SM/13327 | New | Material Requisition To Resource Division |  |  | RTOR000802/2023-2024 | 315/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 17.52 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | MANGANPUR PIPED WATER SUPPLY SCHEME | SM/13327 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MANGANPUR & BAGPUR Piped Water Supply Scheme under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000391/2023-2024 | 3200/BWD | 24/07/2023 | 28/07/2026 | M/S GHOSH & CO. | 711.81 | 180.13 | 25.31 | 10
7 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | MANGANPUR PIPED WATER SUPPLY SCHEME | SM/13327 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at MANGANPUR Water Supply Scheme [Block-PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000730/2023-2024 | 4040/CMD | 29/08/2023 | 28/09/2023 | SOUNAK ENTERPRISE | 22.1 | 10 | 45.24 | 50
8 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | MANGANPUR PIPED WATER SUPPLY SCHEME | SM/13327 | New | Different types of works involve in connection with Augmentation of SRIRAMPUR (Zone I & II) (SM/08103), MANGANPUR (SM/13327), KAMALPUR (SM/13453) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000190/2024-2025 | 2429/BWD | 27/06/2024 | 20/10/2025 | S.P. CONSTRUCTION | 500.89 | 158.83 | 31.71 | 2
9 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | MANGANPUR PIPED WATER SUPPLY SCHEME | SM/13327 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000072/2024-2025 | 2397/CMD | 02/08/2024 | 31/10/2024 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 0 | 30
10 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | MANGANPUR PIPED WATER SUPPLY SCHEME | SM/13327 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000714/2024-2025 | 2979/CMD | 25/11/2024 | 23/02/2025 | H.K. DAS & CO. | 53.27 | 0 | 0 | 0
Total | [13 empty] | 1380.26 | 351.06 | 25.43