## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Manteswar | Burdwan Division | Ground Water Supply Based Piped Water Supply Scheme For DHENUA PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | SM/13331 | New | Material Requisition To Resource Division |  |  | RTOR000244/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 4.24 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Manteswar | Burdwan Division | Ground Water Supply Based Piped Water Supply Scheme For DHENUA PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | SM/13331 | New | Material Requisition To Resource Division |  |  | RTOR000448/2023-2024 | 3972/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 108.75 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Manteswar | Central Mechanical | Ground Water Supply Based Piped Water Supply Scheme For DHENUA PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | SM/13331 | New | NEW SERVICE CONNECTION FOR DHENUA PWSS. |  |  | BILL/02689/2023-2024 | BP-2023-24-564 | 23/02/2024 | 23/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.21 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Manteswar | Central Mechanical | Ground Water Supply Based Piped Water Supply Scheme For DHENUA PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | SM/13331 | New | NEW SERVICE CONNECTION FOR DHENUA PWSS TW -1. |  |  | BILL/03101/2023-2024 | BP-2023-24-641 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.52 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Manteswar | Burdwan Division | Ground Water Supply Based Piped Water Supply Scheme For DHENUA PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | SM/13331 | New | Arrangement of drinking water supply by installation of solar submersible pump including sinking of 200 mm. dia. Tube well 150 Mtr. Deep by direct rotary rig method, Laying dist. System, FHTC and 2 Nos. 5000 Ltr. PVC tank installation with construction of RCC structure for RUIGORIA Habitation which is uncovered of DHENUA Piped W/S. Scheme, Block Manteswar under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE | ORD/000686/2024-2025 | 3667/BWD | 22/10/2024 | 20/01/2025 | UJJWAL MUKHERJEE | 31.83 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Manteswar | Central Mechanical | Ground Water Supply Based Piped Water Supply Scheme For DHENUA PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | SM/13331 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 31/10/2025 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
7 | PURBA BARDHAMAN | Manteswar | Central Mechanical | Ground Water Supply Based Piped Water Supply Scheme For DHENUA PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | SM/13331 | New | CONTINUATION ORDER-Hiring of inspection vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of the Assistant Engineer ,under CMD,PHE,Dte.[W.E.F-31/01/2025 TO 31/03/2025][UNDER JJM WORKS] | ASSISTANT ENGINEER | Junior Engineer | ORD/000778/2024-2025 | 110/CMSD | 30/01/2025 | 31/03/2025 | PRODYUT GHOSH | 0.79 | 0.79 | 100 | 0
8 | PURBA BARDHAMAN | Manteswar | Central Mechanical | Ground Water Supply Based Piped Water Supply Scheme For DHENUA PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | SM/13331 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Dhenua Water Supply Scheme [ Block- Monteshwar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000740/2023-2024 | 4050/CMD | 29/08/2023 | 30/05/2025 | SUBRATA BHADRA | 29.91 | 0 | 0 | 100
Total | [13 empty] | 266.32 | 0.79 | 0.3