## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Katnabil Piped Water Supply Scheme | SM/13338 | New | Material Requisition To Resource Division |  |  | RTOR000375/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 4.23 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Katnabil Piped Water Supply Scheme | SM/13338 | New | Material Requisition To Resource Division |  |  | RTOR000512/2023-2024 | 4036/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 4.83 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Katnabil Piped Water Supply Scheme | SM/13338 | New | Material Requisition To Resource Division |  |  | RTOR000673/2023-2024 | 5050/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Katnabil Piped Water Supply Scheme | SM/13338 | New | New service connection charges for Katnabil PWSS TW-1 |  |  | BILL/01700/2023-2024 | BP-2023-24-231 | 20/11/2023 | 20/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.27 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Katnabil Piped Water Supply Scheme | SM/13338 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 23/12/2024 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Katnabil Piped Water Supply Scheme | SM/13338 | New | New Service connection for Katnabil W/S Scheme PH No.-II |  |  | BILL/01800/2023-2024 | BP-2023-24-300 | 30/12/2023 | 30/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.15 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Katnabil Piped Water Supply Scheme | SM/13338 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to UCHALAN, CHAK CHANDAN, SERPUR & KATNABIL Piped Water Supply Scheme under Raina II Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000367/2023-2024 | 3076/BWD | 18/07/2023 | 01/04/2026 | SK ALIM | 1307.56 | 0 | 0 | 75
8 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Katnabil Piped Water Supply Scheme | SM/13338 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Katnabil Water Supply Scheme [ Block- Raina-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000727/2023-2024 | 4038/CMD | 29/08/2023 | 01/04/2025 | AHALYA ENGINEERING WORKS | 28.95 | 0 | 0 | 96
9 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Katnabil Piped Water Supply Scheme | SM/13338 | New | Supply of various D.I. Mechanical joints & specials for KATNABIL & BANTIR Piped W/S. Scheme within Burdwan Sub-Division under Burdwan Division, PHE. Dte. [Part-B]. | AE(HQs) | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000302/2024-2025 | 2825/BWD | 19/07/2024 | 20/02/2025 | KEJRIWAL CASTINGS LIMITED | 4.82 | 0 | 0 | 100
Total | [13 empty] | 1476.69 | 0 | 0