## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | Material Requisition To Resource Division |  |  | RTOR000068/2022-2023 | 1256/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 6.23 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | Material Requisition To Resource Division |  |  | RTOR000113/2022-2023 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 3.3 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | Material Requisition To Resource Division |  |  | RTOR000721/2023-2024 | 5262/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 21.07 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | New Service Connection charges for Kandarsona W/S Scheme TW-2 |  |  | BILL/00605/2023-2024 | BP-2023-24-12 | 17/05/2023 | 17/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.4 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | New Service Connection charges for Kandarsona W/S Scheme TW-1 |  |  | BILL/00604/2023-2024 | BP-2023-24-11 | 17/05/2023 | 17/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.35 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kandarsona Water Supply Scheme [Block- Burdwan-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000033/2023-2024 | 2471/CMD | 30/05/2023 | 29/06/2023 | DUTTA ENTERPRISE | 28.92 | 23.54 | 81.38 | 80
7 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | Supply & delivery of standby Submersible pumping machinery for Kandarsona & others water supply scheme, under CMD, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/001638/2023-2024 | 823/CMSD | 05/10/2023 | 26/10/2023 | DUTTA ENTERPRISE | 0.84 | 0.84 | 100 | 98
8 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | Re-orientation of delivery pipe line by supply & fitting fixing different CIDF materials, pressure gauge etc. at Kandarsona water supply scheme, T.W. No.- I & II under CMD, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/001707/2023-2024 | 843/CMSD | 18/10/2023 | 28/10/2023 | DUTTA ENTERPRISE | 0.79 | 0.79 | 100 | 99
9 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 31/10/2024 | DILIP MAHATO | 53.14 | 0 | 0 | 12
10 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | Supply and installation of Electro-Magnetic flow meter at HARIGRAM, KUCHUT & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000564/2024-2025 | 3103/CMD | 11/12/2024 | 09/02/2025 | S DUTTA | 15.06 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | KANDARSONA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Burdwan-II Block, District:- Purba-Bardhaman. [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000655/2022-2023 | 358/BWD | 30/01/2023 | 31/12/2024 | M/S S.S. ENTERPRISE | 284.66 | 240.27 | 84.41 | 90
12 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | Beautification of PWSS with Arboriculture, Recharge Pit including shaft and anciliary works) Kandarsona P.W.S.S under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000544/2024-2025 | 279/RWS | 03/09/2024 | 22/12/2024 | M/S PALASH BISWAS | 0.97 | 0 | 0 | 100
13 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | Providing FHTC (due to const. of road by BDA Dept)for Kandarsona PWSS under Bardhaman-II block within Burdwan Div.PHE Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000175/2025-2026 | 1549/BSD | 02/07/2025 | 01/08/2025 | M/S PALASH BISWAS | 0.63 | 0 | 0 | 100
Total | [13 empty] | 423.36 | 265.43 | 62.7