## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan - II | Burdwan Division | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | Material Requisition To Resource Division |  |  | RTOR000068/2022-2023 | 1256/BWD | 17/03/2023 |  | Resource Division | 6.23 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan - II | Burdwan Division | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | Material Requisition To Resource Division |  |  | RTOR000113/2022-2023 | 1962/BWD | 25/04/2023 |  | Resource Division | 3.3 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan - II | Central Mechanical | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | New Service Connection charges for Kandarsona W/S Scheme TW-2 |  |  | BILL/00605/2023-2024 | BP-2023-24-12 | 17/05/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.4 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan - II | Central Mechanical | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | New Service Connection charges for Kandarsona W/S Scheme TW-1 |  |  | BILL/00604/2023-2024 | BP-2023-24-11 | 17/05/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.35 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan - II | Burdwan Division | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | Material Requisition To Resource Division |  |  | RTOR000721/2023-2024 | 5262/BWD | 30/11/2023 |  | Resource Division | 21.07 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan - II | Central Mechanical | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kandarsona Water Supply Scheme [Block- Burdwan-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000033/2023-2024 | 2471/CMD | 30/05/2023 | 29/06/2023 | DUTTA ENTERPRISE | 28.92 | 22.54 | 77.94 | 80
7 | PURBA BARDHAMAN | Burdwan - II | Central Mechanical | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | Re-orientation of delivery pipe line by supply & fitting fixing different CIDF materials, pressure gauge etc. at Kandarsona water supply scheme, T.W. No.- I & II under CMD, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/001707/2023-2024 | 843/CMSD | 18/10/2023 | 28/10/2023 | DUTTA ENTERPRISE | 0.79 | 0.4 | 50 | 99
8 | PURBA BARDHAMAN | Burdwan - II | Central Mechanical | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | Supply & delivery of standby Submersible pumping machinery for Kandarsona & others water supply scheme, under CMD, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/001638/2023-2024 | 823/CMSD | 05/10/2023 | 26/10/2023 | DUTTA ENTERPRISE | 0.84 | 0.42 | 50 | 98
9 | PURBA BARDHAMAN | Burdwan - II | Burdwan Division | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | KANDARSONA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Burdwan-II Block, District:- Purba-Bardhaman. [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000655/2022-2023 | 358/BWD | 30/01/2023 | 30/01/2024 | M/S S.S. ENTERPRISE | 284.66 | 211.31 | 74.23 | 90
10 | PURBA BARDHAMAN | Burdwan - II | Central Mechanical | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 31/10/2024 | DILIP MAHATO | 53.14 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Burdwan - II | Burdwan Division | GROUND WATER BASED KANDARSONA PWSS | SM/13339 | New | Beautification of PWSS with Arboriculture, Recharge Pit including shaft and anciliary works) Kandarsona P.W.S.S under Burdwan Division, PHE Dte. |  | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000544/2024-2025 | 279/RWS | 03/09/2024 | 13/09/2024 | M/S PALASH BISWAS | 0.97 | 0 | 0 | 0
Total | [13 empty] | 407.67 | 234.67 | 57.56