## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Manteswar | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/13340 | New | Material Requisition To Resource Division |  |  | RTOR000241/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 3.1 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Manteswar | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/13340 | New | Material Requisition To Resource Division |  |  | RTOR000596/2023-2024 | 4947/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 35.92 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Manteswar | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/13340 | New | Material Requisition To Resource Division |  |  | RTOR000541/2023-2024 | 4309/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 11.47 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Manteswar | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/13340 | New | Continuation work order for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/08/2024 to 30/09/2024) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000552/2024-2025 | 602/DSD | 30/07/2024 | 29/09/2024 | SUJAUDDIN SEKH | 0.8 | 0 | 0 | 100
5 | PURBA BARDHAMAN | Manteswar | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/13340 | New | Continuation work order for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/10/2024 to 30/11/2024) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000839/2024-2025 | 772/DSD | 18/09/2024 | 18/11/2024 | SUJAUDDIN SEKH | 0.8 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Manteswar | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/13340 | New | NEW SERVICE CONNECTION FOR BELENDA PWSS TW -2. |  |  | BILL/03099/2023-2024 | BP-2023-24-639 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.64 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Manteswar | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/13340 | New | Quotation for new service connection for Belenda PWSS PH 1. |  |  | BILL/00228/2024-2025 | BP-2024-25-119 | 29/05/2024 | 29/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.29 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Manteswar | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/13340 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BELENDA, JAMNA, PIPLON & PARGUNA Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000689/2023-2024 | 4388/BWD | 05/10/2023 | 02/08/2025 | AKASH CONSTRUCTION | 2296.4 | 0 | 0 | 50
9 | PURBA BARDHAMAN | Manteswar | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/13340 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 31/10/2025 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
10 | PURBA BARDHAMAN | Manteswar | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/13340 | New | Continuation work order for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/12/2024 to 31/12/2024) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000994/2024-2025 | 992/DSD | 25/11/2024 | 25/01/2025 | SUJAUDDIN SEKH | 0.4 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Manteswar | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/13340 | New | CONTINUATION ORDER- Hiring of inspection vehicle (Diesel/CNG/LPG Driven)for supervision of site for the office of the Assisatnt Engineer,under CMD,PHE,Dte.[W.E.F-01.04.2025 to 31.05.2025] | ASSISTANT ENGINEER | Junior Engineer | ORD/001173/2024-2025 | 367/CMSD | 26/03/2025 | 26/05/2025 | PRODYUT GHOSH | 0.8 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Manteswar | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/13340 | New | Continuation for Supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Division (Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/04/2025 to 31/05/2025) |  |  | ORD/001513/2024-2025 | 483/DSD | 21/03/2025 | 21/05/2025 | SK ALACK JANDER | 0.8 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Manteswar | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/13340 | New | Supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/02/2025 to 31/03/2025) |  |  | ORD/001508/2024-2025 | 142/DSD | 24/01/2025 | 24/03/2025 | SK ALACK JANDER | 0.8 | 0 | 0 | 0
14 | PURBA BARDHAMAN | Manteswar | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/13340 | New | Work Order for "DESIGNING,MAKING AND ERECTION OF SIGN BOARD FOR SAJAL GRAM IN ¿¿1 No...VILLAGE, ¿MANTESWAR BLOCK UNDER KALNA SUB DIVISION WITHIN BURDWAN DIVISION PHE DTE. (3nos board)" | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001424/2024-2025 | 1920/KSD | 02/12/2024 | 12/12/2024 | OMKAR ENTERPRISE | 0.42 | 0 | 0 | 100
15 | PURBA BARDHAMAN | Manteswar | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/13340 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Belenda Water Supply Scheme [ Block- Monteshwar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000911/2023-2024 | 4175/CMD | 29/08/2023 | 01/08/2025 | SOUNAK ENTERPRISE | 28.48 | 0 | 0 | 95
Total | [13 empty] | 2473.18 | 0 | 0