## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Serpur Piped Water Supply Scheme | SM/13384 | New | Material Requisition To Resource Division |  |  | RTOR000301/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 7.9 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Serpur Piped Water Supply Scheme | SM/13384 | New | Material Requisition To Resource Division |  |  | RTOR000483/2023-2024 | 4007/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 2.05 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Serpur Piped Water Supply Scheme | SM/13384 | New | Material Requisition To Resource Division |  |  | RTOR000692/2023-2024 | 5073/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Serpur Piped Water Supply Scheme | SM/13384 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 23/12/2024 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Serpur Piped Water Supply Scheme | SM/13384 | New | NEW SERVICE CONNECTION FOR SERPUR PWSS PH-2 |  |  | BILL/00107/2024-2025 | BP-2024-25-43 | 26/04/2024 | 26/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.23 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina-II | Central Mechanical | Serpur Piped Water Supply Scheme | SM/13384 | New | New Service connection for Serpur W/S Scheme PH No.-I |  |  | BILL/01797/2023-2024 | BP-2023-24-301 | 30/12/2023 | 30/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.35 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Serpur Piped Water Supply Scheme | SM/13384 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to UCHALAN, CHAK CHANDAN, SERPUR & KATNABIL Piped Water Supply Scheme under Raina II Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000367/2023-2024 | 3076/BWD | 18/07/2023 | 01/10/2025 | SK ALIM | 1307.56 | 147.46 | 11.28 | 75
8 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Serpur Piped Water Supply Scheme | SM/13384 | New | Continuation Work Order for supply of inspection Vehicle No. WB42Y- 7403 for inspection of different JJM related(schemes) works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub Division under Burdwan Division, PHE Dte consider 96.00 Km. run per day (Period from 01-02-2025 to 30-04-2025) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001402/2024-2025 | 240/BSD | 31/01/2025 | 07/04/2025 | PARVIN BEGAM | 0.85 | 0 | 0.15 | 100
9 | PURBA BARDHAMAN | Raina-II | Burdwan Division | Serpur Piped Water Supply Scheme | SM/13384 | New | Continuation Work Order for Supply of one No.Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division,PHE Dte(Period from 01-09-2025 to 30.11.2025) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000693/2025-2026 | 2473/BSD | 29/08/2025 | 28/11/2025 | SK. ASFIA | 1.2 | 0 | 0 | 0
Total | [13 empty] | 1436.01 | 147.46 | 10.27