## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Bhatar,Mangolkote | Burdwan Division | DEBPUR PIPED WATER SUPPLY SCHEME | SM/13398 | New | Material Requisition To Resource Division |  |  | RTOR000087/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 21.04 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Bhatar,Mangolkote | Burdwan Division | DEBPUR PIPED WATER SUPPLY SCHEME | SM/13398 | New | Material Requisition To Resource Division |  |  | RTOR000173/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 20.38 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Bhatar,Mangolkote | Burdwan Division | DEBPUR PIPED WATER SUPPLY SCHEME | SM/13398 | New | Material Requisition To Resource Division |  |  | RTOR000640/2023-2024 | 5106/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.32 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Bhatar,Mangolkote | Central Mechanical | DEBPUR PIPED WATER SUPPLY SCHEME | SM/13398 | New | New service connection charges for Debpur PWSS TW-1 |  |  | BILL/01419/2023-2024 | BP-2023-24-146 | 31/08/2023 | 31/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.73 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Bhatar,Mangolkote | Central Mechanical | DEBPUR PIPED WATER SUPPLY SCHEME | SM/13398 | New | New service connection charges for Debpur PWSS TW-2 |  |  | BILL/01673/2023-2024 | BP-2023-24-224 | 10/11/2023 | 10/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.53 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Bhatar,Mangolkote | Burdwan Division | DEBPUR PIPED WATER SUPPLY SCHEME | SM/13398 | New | Continuation order for Supply of 01(one) No. Diesel Driven Motor Cab (Bharat Stage-II) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Division (Burdwan North) P.H.E. Dte. Govt. of West Bengal (for the period of 01/01/2024 to 31/05/2024) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001180/2023-2024 | 995/DSD | 29/12/2023 | 29/06/2024 | SUJAUDDIN SEKH | 2 | 0.3 | 14.77 | 60
7 | PURBA BARDHAMAN | Bhatar,Mangolkote | Central Mechanical | DEBPUR PIPED WATER SUPPLY SCHEME | SM/13398 | New | Continuation order-Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven ) for supervision of site for the office of the Assistant Engineer,under CMD,PHE,Dte. [W.e.f-29/06/2024 to 31/07/2024] | ASSISTANT ENGINEER | Junior Engineer | ORD/000424/2024-2025 | 897/CMSD | 28/06/2024 | 31/07/2024 | SUBRATA BHADRA | 0.4 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Bhatar,Mangolkote | Central Mechanical | DEBPUR PIPED WATER SUPPLY SCHEME | SM/13398 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 31/10/2024 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Bhatar,Mangolkote | Central Mechanical | DEBPUR PIPED WATER SUPPLY SCHEME | SM/13398 | New | SUPPLY AND INSTALLATION WORKS FOR DEBPUR PWSS |  |  | BILL/02624/2023-2024 | BP-2023-24-557 | 21/02/2024 | 21/02/2024 | P.K. ENGINEERING | 11.09 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Bhatar,Mangolkote | Burdwan Division | DEBPUR PIPED WATER SUPPLY SCHEME | SM/13398 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DHENRIA, MAHATA, DEBPUR Piped Water Supply Scheme under BHATAR Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000019/2023-2024 | 1737/BWD | 13/04/2023 | 31/12/2025 | M/S B. RAI CONSTRUCTION COMPANY | 1643.39 | 317.66 | 19.33 | 81
11 | PURBA BARDHAMAN | Bhatar,Mangolkote | Central Mechanical | DEBPUR PIPED WATER SUPPLY SCHEME | SM/13398 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Debpur Water Supply Scheme [ Block- Bhatar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000232/2023-2024 | 3174/CMD | 26/07/2023 | 25/08/2023 | P.K. ENGINEERING | 27.69 | 10.99 | 39.69 | 95
Total | [13 empty] | 1843.57 | 328.95 | 17.84