## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | ARJUNPUKUR PIPED WATER SUPPLY SCHEME | SM/13413 | New | Material Requisition To Resource Division |  |  | RTOR000177/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 17.1 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | ARJUNPUKUR PIPED WATER SUPPLY SCHEME | SM/13413 | New | Material Requisition To Resource Division |  |  | RTOR000476/2023-2024 | 4000/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 1.54 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | ARJUNPUKUR PIPED WATER SUPPLY SCHEME | SM/13413 | New | New service connection charges for Arjunpukur PWSS Tw-1 |  |  | BILL/00698/2023-2024 | BP-2023-24-50 | 13/07/2023 | 13/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.35 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | ARJUNPUKUR PIPED WATER SUPPLY SCHEME | SM/13413 | New | New service connection charges for Arjunpukur PWSS Tw-2 |  |  | BILL/00699/2023-2024 | BP-2023-24-51 | 13/07/2023 | 13/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.05 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | ARJUNPUKUR PIPED WATER SUPPLY SCHEME | SM/13413 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at ARJUNPUKUR Water Supply Scheme [Block-PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000125/2023-2024 | 2638/CMD | 14/06/2023 | 31/08/2024 | ANJAN ENTERPRISE | 21.51 | 19.5 | 90.68 | 90
6 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | ARJUNPUKUR PIPED WATER SUPPLY SCHEME | SM/13413 | New | Laying of additional pipeline and providing FHTC at ARJUNPUKUR Water Supply Scheme under Kalna Sub-Division, Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000175/2024-2025 | 2252/BWD | 18/06/2024 | 16/09/2024 | IYASIN DAFADAR | 16.6 | 16.6 | 100 | 2
7 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | ARJUNPUKUR PIPED WATER SUPPLY SCHEME | SM/13413 | New | Material Requisition To Resource Division |  |  | RTOR000795/2023-2024 | 314/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 14.63 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | ARJUNPUKUR PIPED WATER SUPPLY SCHEME | SM/13413 | New | Supply and installation of Electro-Magnetic flow meter at Bazar Mahammadpur, Dhatrigram, Arjunpukur & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000590/2024-2025 | 3105/CMD | 11/12/2024 | 09/02/2025 | SHREE BISHNU CONSTRUCTION | 19.77 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | ARJUNPUKUR PIPED WATER SUPPLY SCHEME | SM/13413 | New | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001270/2024-2025 | 849/BWD | 05/03/2025 | 01/09/2025 | S.P. CONSTRUCTION | 683.3 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | ARJUNPUKUR PIPED WATER SUPPLY SCHEME | SM/13413 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000714/2024-2025 | 2979/CMD | 25/11/2024 | 23/02/2025 | H.K. DAS & CO. | 53.27 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | ARJUNPUKUR PIPED WATER SUPPLY SCHEME | SM/13413 | New | Work Order for " Laying distribution system including restorationof FHTC under the command area of Arjunpukur Piped water supply scheme (SM/13413) under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000856/2024-2025 | 1842/KSD | 27/11/2024 | 17/12/2024 | IYASIN DAFADAR | 2.82 | 0 | 0 | 100
12 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | ARJUNPUKUR PIPED WATER SUPPLY SCHEME | SM/13413 | New | ARJUNPUKUR Piped Water Supply Scheme with sinking of Tube-well, LDS,Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000003/2023-2024 | 1617/BWD | 05/04/2023 | 01/01/2025 | AZAD ENTERPRISE | 397.64 | 355.7 | 89.45 | 85
Total | [13 empty] | 1234.57 | 391.81 | 31.74