## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari-I | Burdwan Division | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/13417 | New | Material Requisition To Resource Division |  |  | RTOR000186/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 10.35 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Memari-I | Burdwan Division | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/13417 | New | Material Requisition To Resource Division |  |  | RTOR000411/2023-2024 | 3869/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 8.83 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Memari-I | Burdwan Division | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/13417 | New | Material Requisition To Resource Division |  |  | RTOR000749/2023-2024 | 5250/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 20.21 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari-I | Central Mechanical | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/13417 | New | New service connection charges for Durgadanga PWSS TW-1 |  |  | BILL/01262/2023-2024 | BP-2023-24-122 | 17/08/2023 | 17/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.07 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Memari-I | Central Mechanical | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/13417 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 31/10/2024 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Memari-I | Burdwan Division | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/13417 | New | DURGADANGA Single Village Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000010/2023-2024 | 1714/BWD | 12/04/2023 | 11/07/2023 | A R TRADERS | 57.63 | 57.42 | 99.62 | 100
7 | PURBA BARDHAMAN | Memari-I | Burdwan Division | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/13417 | New | Sinking of Tube-well, construction of switch rooms & Rising main at 2ND TW site for DURGADANGA Piped Water Supply Scheme under MEMARI-I Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000868/2023-2024 | 5307/BWD | 01/12/2023 | 30/01/2024 | A R TRADERS | 21.69 | 20.71 | 95.47 | 100
8 | PURBA BARDHAMAN | Memari-I | Burdwan Division | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/13417 | New | Allied work of Laying distribution system for FHTC work for DURGADANGA Piped Water Supply Scheme at Durgadanga mouza within MEMARI - I Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001017/2023-2024 | 521/BWD | 06/02/2024 | 07/03/2024 | A R TRADERS | 13.36 | 13.34 | 99.83 | 100
9 | PURBA BARDHAMAN | Memari-I | Central Mechanical | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/13417 | New | NEW SERVICE CONNECTION FOR DURGADANGA PWSS |  |  | BILL/02838/2023-2024 | BP-2023-24-587 | 04/03/2024 | 04/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.12 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Memari-I | Burdwan Division | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/13417 | New | Restoration of concrete road by Cement concrete (mix 1:1.5:3),Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for DURGADANGA SVS & DEHA PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001039/2024-2025 | 141/BWD | 08/01/2025 | 08/04/2025 | MUKHERJEE ENTERPRISE | 64.37 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Memari-I | Burdwan Division | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/13417 | New | Construction of Boundary wall at HEAD WORK Site & 2nd TW site & Culvert at Head work site & Interconnection between Head work site distribution line 2nd Tw site of DURGADANGA Piped Water Supply Scheme under MEMARI-I Block of Burdwan Division, PHE Dte. (Length -164.00 Mtr, Col-66 Nos). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000321/2024-2025 | 2857/BWD | 22/07/2024 | 02/11/2025 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 29.26 | 0 | 0 | 50
12 | PURBA BARDHAMAN | Memari-I | Central Mechanical | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/13417 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Durgadanga Water Supply Scheme [ Block- Memari-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000139/2023-2024 | 2820/CMD | 04/07/2023 | 03/08/2023 | C.M. ENTERPRISE | 29.33 | 23.71 | 80.85 | 95
Total | [13 empty] | 309.85 | 115.18 | 37.17