## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | KONRAPUR PIPED WATER SUPPLY SCHEME | SM/13419 | New | Material Requisition To Resource Division |  |  | RTOR000471/2023-2024 | 3995/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 11.87 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | KONRAPUR PIPED WATER SUPPLY SCHEME | SM/13419 | New | Material Requisition To Resource Division |  |  | RTOR000161/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 8.28 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | KONRAPUR PIPED WATER SUPPLY SCHEME | SM/13419 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KONRAPUR & MASGARIA Piped Water Supply Scheme under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000026/2023-2024 | 1765/BWD | 17/04/2023 | 16/04/2024 | M/S ASHA CONSTRUCTION | 710.72 | 123.45 | 17.37 | 43
4 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | KONRAPUR PIPED WATER SUPPLY SCHEME | SM/13419 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at KONRAPUR Water Supply Scheme [Block-PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001056/2023-2024 | 4198/CMD | 29/08/2023 | 28/09/2023 | MITRA ASSOCIATES | 21.47 | 9.64 | 44.88 | 50
5 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | KONRAPUR PIPED WATER SUPPLY SCHEME | SM/13419 | New | Material Requisition To Resource Division |  |  | RTOR000800/2023-2024 | 309/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 16.1 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | KONRAPUR PIPED WATER SUPPLY SCHEME | SM/13419 | New | NEW SERVICE CONNECTION FOR KONRAPUR PWSS |  |  | BILL/02694/2023-2024 | BP-2023-24-567 | 27/02/2024 | 27/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.54 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | KONRAPUR PIPED WATER SUPPLY SCHEME | SM/13419 | New | NEW SERVICE CONNECTION FOR KONRAPUR PWSS. |  |  | BILL/02695/2023-2024 | BP-2023-24-568 | 27/02/2024 | 27/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12.76 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | KONRAPUR PIPED WATER SUPPLY SCHEME | SM/13419 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000072/2024-2025 | 2397/CMD | 02/08/2024 | 31/10/2024 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 0 | 30
9 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | KONRAPUR PIPED WATER SUPPLY SCHEME | SM/13419 | New | Different types of balance works involve in connection with KONRAPUR (SM/13419) & MASGORIA (SM/13318) Piped water supply scheme under Purbasthali-I Block within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001028/2024-2025 | 142/BWD | 08/01/2025 | 08/05/2025 | M/S ASHA CONSTRUCTION | 65.74 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | KONRAPUR PIPED WATER SUPPLY SCHEME | SM/13419 | New | Material Requisition To Resource Division |  |  | RTOR000056/2024-2025 | 419/BWD | 17/01/2025 | 17/01/2025 | Resource Division | 1.8 | 0 | 0 | 0
Total | [13 empty] | 900.87 | 133.08 | 14.77