## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | BICHKHARA PIPED WATER SUPPLY SCHEME | SM/13422 | New | Material Requisition To Resource Division |  |  | RTOR000077/2022-2023 | 1265/BWD | 17/03/2023 |  | Resource Division | 2.71 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | BICHKHARA PIPED WATER SUPPLY SCHEME | SM/13422 | New | Material Requisition To Resource Division |  |  | RTOR000098/2022-2023 | 1962/BWD | 25/04/2023 |  | Resource Division | 2.14 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | BICHKHARA PIPED WATER SUPPLY SCHEME | SM/13422 | New | New service connection charges for Bichkhara W/S Scheme TW-1 |  |  | BILL/00683/2023-2024 | BP-2023-24-29 | 22/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.61 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | BICHKHARA PIPED WATER SUPPLY SCHEME | SM/13422 | New | New service connection charges for Bichkhara W/S Scheme TW-2 |  |  | BILL/00684/2023-2024 | BP-2023-24-30 | 22/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.64 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | BICHKHARA PIPED WATER SUPPLY SCHEME | SM/13422 | New | Material Requisition To Resource Division |  |  | RTOR000711/2023-2024 | 5042/BWD | 23/11/2023 |  | Resource Division | 20.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | BICHKHARA PIPED WATER SUPPLY SCHEME | SM/13422 | New | BICHKHARA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch-rooms & boundary walls at different TW site under KHANDOGHOSH Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000638/2022-2023 | 253/BWD | 16/01/2023 | 15/07/2023 | KOUSIK MALLICK | 121.67 | 76.18 | 62.61 | 90
7 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | BICHKHARA PIPED WATER SUPPLY SCHEME | SM/13422 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bichkhara Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000042/2023-2024 | 2494/CMD | 01/06/2023 | 01/07/2023 | CONCORD ENGINEERING | 28.89 | 23.37 | 80.89 | 98
8 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | BICHKHARA PIPED WATER SUPPLY SCHEME | SM/13422 | New | Supply & delivery of standby Submersible pumping machinery & automatic Chlorinator for Bichkhara & others water supply scheme, under CMD, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/001408/2023-2024 | 149/CMSD | 22/01/2024 | 06/02/2024 | CHOUDHURY ENTERPRISE | 1.76 | 0.88 | 50 | 100
9 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | BICHKHARA PIPED WATER SUPPLY SCHEME | SM/13422 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 31/10/2024 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
Total | [13 empty] | 229.41 | 100.42 | 43.77