## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13424 | New | Material Requisition To Resource Division |  |  | RTOR000073/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 3.93 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13424 | New | Material Requisition To Resource Division |  |  | RTOR000175/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 13.07 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13424 | New | Material Requisition To Resource Division |  |  | RTOR000716/2023-2024 | 5268/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 21.07 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13424 | New | New service connection charges for Guir PWSS TW 1 |  |  | BILL/00817/2023-2024 | BP-2023-24-96 | 02/08/2023 | 02/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.97 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13424 | New | New service connection charges for Guir PWSS TW-2 |  |  | BILL/00799/2023-2024 | BP-2023-24-84 | 26/07/2023 | 26/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.96 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13424 | New | GUIR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte.,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000018/2023-2024 | 1732/BWD | 13/04/2023 | 01/01/2025 | UNIQUE AGENCY | 531.21 | 153 | 28.8 | 40
7 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13424 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 31/10/2024 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13424 | New | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.consider 96.00 Km. run per day [Period February'2024 to April'2024] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001233/2023-2024 | 91/DSD | 31/01/2024 | 18/04/2024 | MD HASIN | 1 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13424 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period May'2024 to July'2024] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000255/2024-2025 | 369/DSD | 30/04/2024 | 17/07/2024 | MD HASIN | 1 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13424 | New | Balance work for providing Functional Household Tap Connection (FHTC) within the command area KHEJURHATI & GUIR W/S. Scheme of Khandaghosh Block under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/001217/2024-2025 | 724/BWD | 24/02/2025 | 24/06/2025 | ROY CONSTRUCTION | 153.99 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13424 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Guir Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000142/2023-2024 | 2855/CMD | 05/07/2023 | 04/08/2023 | M/S GHOSH ENTERPRISE | 28.95 | 0 | 0 | 90
Total | [13 empty] | 811.69 | 153 | 18.85