## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari - I | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | Material Requisition To Resource Division |  |  | RTOR000067/2022-2023 | 1262/BWD | 17/03/2023 |  | Resource Division | 7.32 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Memari - I | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | New Service Connection charges for Sahapur W/S Scheme TW-1 |  |  | BILL/00602/2023-2024 | BP-2023-24-13 | 17/05/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.9 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Memari - I | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | New Service Connection charges for Sahapur W/S Scheme TW-2 |  |  | BILL/00603/2023-2024 | BP-2023-24-14 | 17/05/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.08 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari - I | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | Material Requisition To Resource Division |  |  | RTOR000500/2023-2024 | 4024/BWD | 08/09/2023 |  | Resource Division | 2.93 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Memari - I | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | Material Requisition To Resource Division |  |  | RTOR000690/2023-2024 | 5074/BWD | 23/11/2023 |  | Resource Division | 20.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Memari - I | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sahapur Water Supply Scheme [Block- Memari-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000037/2023-2024 | 2480/CMD | 31/05/2023 | 30/06/2023 | P.K. ENGINEERING | 29.29 | 23.01 | 78.55 | 98
7 | PURBA BARDHAMAN | Memari - I | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | SAHAPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Memari-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000636/2022-2023 | 82/BWD | 09/01/2023 | 09/01/2024 | S.K. CONSTRUCTION | 256.31 | 233.94 | 91.27 | 100
8 | PURBA BARDHAMAN | Memari - I | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | Rest portion of OHR (Plaster, Painting and interconnection of Rising Main with Specials) at SAHAPUR Piped Water Supply Scheme under Memari-I Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000188/2024-2025 | 2419/BWD | 27/06/2024 | 25/09/2024 | S.K. CONSTRUCTION | 20.6 | 7.53 | 36.54 | 0
9 | PURBA BARDHAMAN | Memari - I | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 31/10/2024 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
Total | [13 empty] | 390.51 | 264.47 | 67.73