## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari-I | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | SAHAPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Memari-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000636/2022-2023 | 82/BWD | 09/01/2023 | 09/01/2024 | S.K. CONSTRUCTION | 256.31 | 256.03 | 99.89 | 100
2 | PURBA BARDHAMAN | Memari-I | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sahapur Water Supply Scheme [Block- Memari-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000037/2023-2024 | 2480/CMD | 31/05/2023 | 30/06/2023 | P.K. ENGINEERING | 29.29 | 24 | 81.95 | 98
3 | PURBA BARDHAMAN | Memari-I | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | Material Requisition To Resource Division |  |  | RTOR000067/2022-2023 | 1262/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 7.32 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari-I | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | Material Requisition To Resource Division |  |  | RTOR000500/2023-2024 | 4024/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 2.93 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Memari-I | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | Material Requisition To Resource Division |  |  | RTOR000690/2023-2024 | 5074/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Memari-I | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | New Service Connection charges for Sahapur W/S Scheme TW-2 |  |  | BILL/00603/2023-2024 | BP-2023-24-14 | 17/05/2023 | 17/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.08 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Memari-I | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | New Service Connection charges for Sahapur W/S Scheme TW-1 |  |  | BILL/00602/2023-2024 | BP-2023-24-13 | 17/05/2023 | 17/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.9 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Memari-I | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | AE(HQs),Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 01/04/2026 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 0 | 85
9 | PURBA BARDHAMAN | Memari-I | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 31/10/2024 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Memari-I | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | Rest portion of OHR (Plaster, Painting and interconnection of Rising Main with Specials) at SAHAPUR Piped Water Supply Scheme under Memari-I Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000188/2024-2025 | 2419/BWD | 27/06/2024 | 25/09/2024 | S.K. CONSTRUCTION | 20.6 | 13.33 | 64.7 | 100
11 | PURBA BARDHAMAN | Memari-I | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | Designing, making and erection of Sign Board for SWAJAL GRAM in Sekhpur village of Memari-I Block under Sahapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte (5 nos Board) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000614/2025-2026 | 2370/BSD | 21/08/2025 | 31/08/2025 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Memari-I | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | Designing,making and erection of Sign Board for SWAJAL GRAM in Nagarkona village of Memari-I Block under Sahapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte (5 Nos. Board) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000441/2025-2026 | 2306/BSD | 19/08/2025 | 29/08/2025 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Memari-I | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/13425 | New | Designing, making and erection of Sign Board for SWAJAL GRAM in Sahapur village of Memari-I Block under Sahapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte(5 nos Board) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000471/2025-2026 | 2337/BSD | 21/08/2025 | 31/08/2025 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0 | 0
Total | [13 empty] | 702.28 | 293.36 | 41.77