## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari-I | Burdwan Division | BIJRA PIPED WATER SUPPLY SCHEME | SM/13426 | New | Material Requisition To Resource Division |  |  | RTOR000464/2023-2024 | 3988/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 1.04 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Memari-I | Burdwan Division | BIJRA PIPED WATER SUPPLY SCHEME | SM/13426 | New | Material Requisition To Resource Division |  |  | RTOR000260/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 16.43 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Memari-I | Burdwan Division | BIJRA PIPED WATER SUPPLY SCHEME | SM/13426 | New | Material Requisition To Resource Division |  |  | RTOR000657/2023-2024 | 5115/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari-I | Burdwan Division | BIJRA PIPED WATER SUPPLY SCHEME | SM/13426 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte." [Period from 01.12.2023 to 31.01.2024] | AE(HQs) | J.E. 1 BURDWAN | ORD/001207/2023-2024 | 921/AE/HQ | 30/11/2023 | 31/01/2024 | SOURAV JANA | 0.8 | 0.8 | 99.85 | 50
5 | PURBA BARDHAMAN | Memari-I | Central Mechanical | BIJRA PIPED WATER SUPPLY SCHEME | SM/13426 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 31/10/2024 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Memari-I | Central Mechanical | BIJRA PIPED WATER SUPPLY SCHEME | SM/13426 | New | New electric connection for Bijra PWSS, PH-2. |  |  | BILL/01876/2023-2024 | BP-2023-24-342 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.97 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Memari-I | Central Mechanical | BIJRA PIPED WATER SUPPLY SCHEME | SM/13426 | New | Additional quotation for new service connection at Bijra PWSS |  |  | BILL/01027/2024-2025 | BP-2024-25-383 | 14/11/2024 | 14/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.24 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Memari-I | Central Mechanical | BIJRA PIPED WATER SUPPLY SCHEME | SM/13426 | New | Electric quotation for New Service Connection at Bijra W/S Scehem PH-I. |  |  | BILL/01779/2023-2024 | BP-2023-24-282 | 26/12/2023 | 26/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.34 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Memari-I | Central Mechanical | BIJRA PIPED WATER SUPPLY SCHEME | SM/13426 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BIJRA Water Supply Scheme [ Block- MEMARI-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000806/2023-2024 | 4091/CMD | 29/08/2023 | 01/01/2025 | ORIENTAL ENGINEERING CO. | 29.39 | 0 | 0 | 100
10 | PURBA BARDHAMAN | Memari-I | Burdwan Division | BIJRA PIPED WATER SUPPLY SCHEME | SM/13426 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEHA & BIJRA Piped Water Supply Scheme under Memari I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000092/2023-2024 | 2215/BWD | 15/05/2023 | 01/04/2026 | CONCORD ENGINEERING | 868.87 | 167.92 | 19.33 | 60
Total | [13 empty] | 999.17 | 168.72 | 16.89