## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | Material Requisition To Resource Division |  |  | RTOR000076/2022-2023 | 1254/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 4.93 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | Material Requisition To Resource Division |  |  | RTOR000104/2022-2023 | 1634/BWD | 06/04/2023 | 06/04/2023 | Resource Division | 0.76 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | Material Requisition To Resource Division |  |  | RTOR000704/2023-2024 | 5039/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | Shifting of 25KVA DTR at Punshur Water Supply Scheme |  |  | BILL/00608/2023-2024 | BP-2023-24-17 | 02/06/2023 | 02/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.88 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | New service connection charges of Punshur W/S Scheme TW-2 |  |  | BILL/00677/2023-2024 | BP-2023-24-22 | 21/06/2023 | 21/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.8 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | New service connection charges of Punshur W/S Scheme TW-1 |  |  | BILL/00676/2023-2024 | BP-2023-24-21 | 21/06/2023 | 21/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.29 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | PUNSUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under KHANDOGOSH Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte.,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000637/2022-2023 | 162/BWD | 11/01/2023 | 11/01/2024 | TIRUPATI ENTERPRISES | 278.54 | 157.59 | 56.58 | 75
8 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 31/10/2024 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Punsur Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000043/2023-2024 | 2495/CMD | 01/06/2023 | 01/07/2023 | M/S. SWAPAN BANERJEE | 28.94 | 11.94 | 41.25 | 100
10 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | Supply & installation works for Punsur PWSS. |  |  | BILL/02564/2023-2024 | BP-2023-24-547 | 20/02/2024 | 20/02/2024 | M/S. SWAPAN BANERJEE | 11.87 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.consider 96.00 Km. run per day [Period February'2024 to April'2024] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001233/2023-2024 | 91/DSD | 31/01/2024 | 18/04/2024 | MD HASIN | 1 | 0.29 | 29.49 | 0
12 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period May'2024 to July'2024] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000255/2024-2025 | 369/DSD | 30/04/2024 | 17/07/2024 | MD HASIN | 1 | 0.33 | 33.33 | 0
13 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | AE(HQs),Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 01/07/2025 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 0 | 85
Total | [13 empty] | 712.6 | 170.15 | 23.88