## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | Material Requisition To Resource Division |  |  | RTOR000076/2022-2023 | 1254/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 4.93 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | Material Requisition To Resource Division |  |  | RTOR000104/2022-2023 | 1634/BWD | 06/04/2023 | 06/04/2023 | Resource Division | 0.76 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | Material Requisition To Resource Division |  |  | RTOR000704/2023-2024 | 5039/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | Shifting of 25KVA DTR at Punshur Water Supply Scheme |  |  | BILL/00608/2023-2024 | BP-2023-24-17 | 02/06/2023 | 02/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.88 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | New service connection charges of Punshur W/S Scheme TW-2 |  |  | BILL/00677/2023-2024 | BP-2023-24-22 | 21/06/2023 | 21/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.8 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | New service connection charges of Punshur W/S Scheme TW-1 |  |  | BILL/00676/2023-2024 | BP-2023-24-21 | 21/06/2023 | 21/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.29 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | PUNSUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under KHANDOGOSH Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte.,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000637/2022-2023 | 162/BWD | 11/01/2023 | 11/01/2024 | TIRUPATI ENTERPRISES | 278.54 | 157.59 | 56.58 | 75
8 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 31/10/2024 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Punsur Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000043/2023-2024 | 2495/CMD | 01/06/2023 | 01/07/2023 | M/S. SWAPAN BANERJEE | 28.94 | 11.94 | 41.25 | 100
10 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | Supply & installation works for Punsur PWSS. |  |  | BILL/02564/2023-2024 | BP-2023-24-547 | 20/02/2024 | 20/02/2024 | M/S. SWAPAN BANERJEE | 11.87 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.consider 96.00 Km. run per day [Period February'2024 to April'2024] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001233/2023-2024 | 91/DSD | 31/01/2024 | 18/04/2024 | MD HASIN | 1 | 0.29 | 29.49 | 0
12 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK | SM/13450 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period May'2024 to July'2024] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000255/2024-2025 | 369/DSD | 30/04/2024 | 17/07/2024 | MD HASIN | 1 | 0.33 | 33.33 | 0
Total | [13 empty] | 403 | 170.15 | 42.22