## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | KAMALPUR PIPED WATER SUPPLY SCHEME | SM/13453 | New | Material Requisition To Resource Division |  |  | RTOR000502/2023-2024 | 4026/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 0.98 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | KAMALPUR PIPED WATER SUPPLY SCHEME | SM/13453 | New | New service connection charges for Kamalpur PWSS TW-1 |  |  | BILL/02215/2023-2024 | BP-2023-24-388 | 17/01/2024 | 17/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.38 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | KAMALPUR PIPED WATER SUPPLY SCHEME | SM/13453 | New | New service connection for KAMALPUR PWSS TW-2. |  |  | BILL/02399/2023-2024 | BP-2023-24-501 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.24 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | KAMALPUR PIPED WATER SUPPLY SCHEME | SM/13453 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KACHUA & KAMALPUR Piped Water Supply Scheme under Purbasthali ¿ I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000133/2023-2024 | 2344/BWD | 22/05/2023 | 01/10/2025 | CONCORD ENGINEERING | 470.92 | 0 | 0 | 40
5 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | KAMALPUR PIPED WATER SUPPLY SCHEME | SM/13453 | New | Different types of works involve in connection with Augmentation of SRIRAMPUR (Zone I & II) (SM/08103), MANGANPUR (SM/13327), KAMALPUR (SM/13453) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000190/2024-2025 | 2429/BWD | 27/06/2024 | 20/10/2025 | S.P. CONSTRUCTION | 500.89 | 0 | 0 | 2
6 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | KAMALPUR PIPED WATER SUPPLY SCHEME | SM/13453 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at KAMALPUR Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000813/2023-2024 | 4095/CMD | 29/08/2023 | 29/01/2025 | MUKHERJEE ART CENTRE | 21.4 | 0 | 0 | 100
Total | [13 empty] | 1002.81 | 0 | 0