## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | TELUN PIPED WATER SUPPLY SCHEME | SM/13455 | New | TELUN Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KHANDAGHOSH Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte.,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000803/2022-2023 | 1535/BWD | 29/03/2023 | 05/11/2025 | G.B. CONSTRUCTION & CO. | 449.21 | 96.91 | 21.57 | 30
2 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | TELUN PIPED WATER SUPPLY SCHEME | SM/13455 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Telun Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000907/2023-2024 | 4171/CMD | 29/08/2023 | 28/09/2023 | P.K. ENGINEERING | 29.82 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | TELUN PIPED WATER SUPPLY SCHEME | SM/13455 | New | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 7.19 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | TELUN PIPED WATER SUPPLY SCHEME | SM/13455 | New | Material Requisition To Resource Division |  |  | RTOR000168/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 13.11 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | TELUN PIPED WATER SUPPLY SCHEME | SM/13455 | New | Material Requisition To Resource Division |  |  | RTOR000735/2023-2024 | 5258/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 21.07 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | TELUN PIPED WATER SUPPLY SCHEME | SM/13455 | New | Quotation for new service connection at TELUN W/S Scheme PH-II. |  |  | BILL/01811/2023-2024 | BP-2023-24-302 | 30/12/2023 | 30/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.25 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | TELUN PIPED WATER SUPPLY SCHEME | SM/13455 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 31/10/2024 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | TELUN PIPED WATER SUPPLY SCHEME | SM/13455 | New | New service connection charges for Telun PWSS TW-1 |  |  | BILL/02208/2023-2024 | BP-2023-24-392 | 17/01/2024 | 17/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.9 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | TELUN PIPED WATER SUPPLY SCHEME | SM/13455 | New | Balance work for providing Functional Household Tap Connection (FHTC) within the command area BICHKHARA & TELUN W/S. Scheme of Khandaghosh Block under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001096/2024-2025 | 434/BWD | 20/01/2025 | 21/07/2025 | KOUSIK MALLICK | 108.55 | 0 | 0 | 50
10 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | TELUN PIPED WATER SUPPLY SCHEME | SM/13455 | New | Land demarcation and preparation of sketch map including legal charges for different PWSS under JJM of Khandaghosh Block under Duragapur (Burdwan North) Sub-Division, P.H.E. DTE. [Part-A] |  |  | ORD/001510/2024-2025 | 158/DSD | 27/01/2025 | 26/07/2025 | SHUBHRA KANTI GHOSH | 0.81 | 0 | 0 | 90
11 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | TELUN PIPED WATER SUPPLY SCHEME | SM/13455 | New | Mutation of Departmental Land use in various PWSS (Existing & New) under JJM of Bhatar, Khandaghosh and Manteswar Block under Duragapur (Burdwan North) Sub-Division, P.H.E. DTE. |  | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000237/2025-2026 | 661/DSD | 30/04/2025 | 30/04/2026 | SHUBHRA KANTI GHOSH | 0.47 | 0 | 0 | 70
Total | [13 empty] | 688.91 | 96.91 | 14.07