## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | BALABATI PIPED WATER SUPPLY SCHEME | SM/13457 | New | Material Requisition To Resource Division |  |  | RTOR000076/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 2.2 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | BALABATI PIPED WATER SUPPLY SCHEME | SM/13457 | New | Material Requisition To Resource Division |  |  | RTOR000167/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 9.06 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | BALABATI PIPED WATER SUPPLY SCHEME | SM/13457 | New | Material Requisition To Resource Division |  |  | RTOR000709/2023-2024 | 5048/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | BALABATI PIPED WATER SUPPLY SCHEME | SM/13457 | New | New service connection charges for Balabati PWSS TW-1 |  |  | BILL/01777/2023-2024 | BP-2023-24-283 | 26/12/2023 | 26/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.89 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | BALABATI PIPED WATER SUPPLY SCHEME | SM/13457 | New | Electric quotation for New Service Connection at Balabati W/S Scehem PH-2. |  |  | BILL/01773/2023-2024 | BP-2023-24-284 | 26/12/2023 | 26/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.71 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | BALABATI PIPED WATER SUPPLY SCHEME | SM/13457 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMRA, BALABATI, UKHRID & RUPSA Piped Water Supply Scheme under KHANDAGHOSH Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte.,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000008/2023-2024 | 1726/BWD | 13/04/2023 | 01/10/2025 | S.P. CONSTRUCTION | 1710.27 | 271.5 | 15.87 | 45
7 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | BALABATI PIPED WATER SUPPLY SCHEME | SM/13457 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000071/2024-2025 | 2391/CMD | 02/08/2024 | 31/10/2024 | C.M. ENTERPRISE | 45.81 | 0 | 0 | 10
8 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | BALABATI PIPED WATER SUPPLY SCHEME | SM/13457 | New | Balance work for providing Functional Household Tap Connection (FHTC) within the command area BALABATI, AMRA & RUPSA W/S. Scheme of Khandaghosh Block under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001189/2024-2025 | 609/BWD | 11/02/2025 | 11/06/2025 | M/S S.S. ENTERPRISE | 194.58 | 0 | 0 | 0
Total | [13 empty] | 1989.96 | 271.5 | 13.64