## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari-II | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | New | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/08/2023 to 31/10/2023] |  |  | ORD/000845/2023-2024 | 1759/BSD | 28/07/2023 | 02/10/2023 | MD HASIN | 0.85 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Memari-II | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | New | Supply & delivery of different dia. MJ Coller for FHTC as well as smooth running of different W/S. Schemes under Burdwan Division, P.H.E. Dte. [i.e. (1) Magra PWSS, Memari-I Block, (2) Kuchut PWSS, Memari - II Block, (3) Khundkuri PWSS, Khandaghosh Block & (4) Samanti PWSS, Burdwan - II Block)] |  |  | ORD/000653/2023-2024 | 4076/BWD | 13/09/2023 | 03/10/2023 | SSPR VALVE MANUFACTURING PVT LTD. | 20.63 | 5 | 24.24 | 100
3 | PURBA BARDHAMAN | Memari-II | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | New | Material Requisition To Resource Division |  |  | RTOR000072/2022-2023 | 1269/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 14.2 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari-II | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | New | Material Requisition To Resource Division |  |  | RTOR000466/2023-2024 | 3990/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 1.7 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Memari-II | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | New | Material Requisition To Resource Division |  |  | RTOR000674/2023-2024 | 5051/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Memari-II | Central Mechanical | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | New | New service connection charges for Kuchut PWSS TW-1 |  |  | BILL/00778/2023-2024 | BP-2023-24-77 | 24/07/2023 | 24/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.87 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Memari-II | Central Mechanical | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | New | New service connection charges for Kuchut PWSS TW-2 |  |  | BILL/00779/2023-2024 | BP-2023-24-78 | 24/07/2023 | 24/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.83 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Memari-II | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.06.2024 to 31.07.2024] | AE(HQs) | J.E. 1 BURDWAN | ORD/000440/2024-2025 | 305/AE/HQ | 31/05/2024 | 31/07/2024 | SOURAV JANA | 0.8 | 0.8 | 99.91 | 0
9 | PURBA BARDHAMAN | Memari-II | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.10.2024 to 30.11.2024] | AE(HQs) | Contractual Junior Engineer | ORD/000706/2024-2025 | 822/AE/HQ | 01/10/2024 | 01/12/2024 | SOURAV JANA | 0.8 | 0.76 | 94.95 | 0
10 | PURBA BARDHAMAN | Memari-II | Central Mechanical | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000102/2024-2025 | 2395/CMD | 02/08/2024 | 31/10/2024 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Memari-II | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | New | Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.02.2024 to 31.03.2024] | AE(HQs) | J.E. 1 BURDWAN | ORD/001203/2023-2024 | 41/AE/HQ | 29/01/2024 | 29/03/2024 | SOURAV JANA | 0.8 | 0.8 | 99.69 | 50
12 | PURBA BARDHAMAN | Memari-II | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.04.2024 to 31.05.2024] | AE(HQs) | J.E. 1 BURDWAN | ORD/001229/2023-2024 | 232/AE/HQ | 28/03/2024 | 28/05/2024 | SOURAV JANA | 0.8 | 0.8 | 99.87 | 0
13 | PURBA BARDHAMAN | Memari-II | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.08.2024 to 30.09.2024] | AE(HQs) | Contractual Junior Engineer | ORD/000505/2024-2025 | 546/AE/HQ | 01/08/2024 | 01/10/2024 | SOURAV JANA | 0.8 | 0.8 | 99.97 | 0
14 | PURBA BARDHAMAN | Memari-II | Central Mechanical | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kuchut Water Supply Scheme [ Block- Memari-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000050/2023-2024 | 2512/CMD | 02/06/2023 | 02/07/2023 | CHOUDHURY ENTERPRISE | 29.4 | 24.17 | 82.23 | 50
15 | PURBA BARDHAMAN | Memari-II | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.12.2024 to 31.01.2025] | AE(HQs) | Contractual Junior Engineer | ORD/000898/2024-2025 | 1011/AE/HQ | 29/11/2024 | 29/01/2025 | SOURAV JANA | 0.8 | 0.8 | 99.62 | 0
16 | PURBA BARDHAMAN | Memari-II | Central Mechanical | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | New | Supply and installation of Electro-Magnetic flow meter at HARIGRAM, KUCHUT & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000564/2024-2025 | 3103/CMD | 11/12/2024 | 09/02/2025 | S DUTTA | 15.06 | 0 | 0 | 0
17 | PURBA BARDHAMAN | Memari-II | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.02.2025 to 31.03.2025] | AE(HQs) | Contractual Junior Engineer | ORD/001156/2024-2025 | 184/AE/HQ | 31/01/2025 | 31/03/2025 | SOURAV JANA | 0.8 | 0.8 | 99.8 | 0
18 | PURBA BARDHAMAN | Memari-II | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | New | Different Types of work involved in connection with different New Schemes (05 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000003/2025-2026 | 1116/BWD | 03/04/2025 | 01/08/2025 | SOFIQUL ISLAM | 176.89 | 0 | 0 | 0
19 | PURBA BARDHAMAN | Memari-II | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.04.2025 to 31.05.2025] | AE(HQs) | Contractual Junior Engineer | ORD/001403/2024-2025 | 454/AE/HQ | 28/03/2025 | 28/05/2025 | SOURAV JANA | 0.8 | 0.4 | 49.93 | 0
20 | PURBA BARDHAMAN | Memari-II | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | New | Repairing damaged Pipeline & concrete road by Cement concrete (mix 1:1.5:3) and drainage system, Sluice valve chamber for FHTC work for SATGACHIA ZONE-I, SATGACHIA ZONE-II, SRIDHARPUR, PARHATI, KUCHUT, NOAHATI, MONDALGRAM PWSS and its adjoining mouzas within MEMARI-II BLOCK under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000283/2024-2025 | 2715/BWD | 11/07/2024 | 01/02/2025 | A.R. TRADERS | 74.28 | 15.36 | 20.68 | 100
21 | PURBA BARDHAMAN | Memari-II | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME | SM/13464 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KUCHUT & NOAHATI Piped Water Supply Scheme under Memari - II Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000750/2022-2023 | 1172/BWD | 14/03/2023 | 31/03/2026 | NATIONAL CONSTRUCTION | 831.75 | 354.66 | 42.64 | 99
Total | [13 empty] | 1235.31 | 405.14 | 32.8