## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | Material Requisition To Resource Division |  |  | RTOR000074/2022-2023 | 1253/BWD | 17/03/2023 |  | Resource Division | 16.58 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | Material Requisition To Resource Division |  |  | RTOR000106/2022-2023 | 1631/BWD | 06/04/2023 |  | Resource Division | 12.19 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | New service connection charges for Khundkuri PWSS TW-1 |  |  | BILL/01035/2023-2024 | BP-2023-24-115 | 16/08/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.93 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | New service connection charges for Khundkuri PWSS TW-2 |  |  | BILL/01036/2023-2024 | BP-2023-24-116 | 16/08/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.65 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | Material Requisition To Resource Division |  |  | RTOR000705/2023-2024 | 5046/BWD | 23/11/2023 |  | Resource Division | 20.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | Supply & delivery of different dia. MJ Coller for FHTC as well as smooth running of different W/S. Schemes under Burdwan Division, P.H.E. Dte. [i.e. (1) Magra PWSS, Memari-I Block, (2) Kuchut PWSS, Memari - II Block, (3) Khundkuri PWSS, Khandaghosh Block & (4) Samanti PWSS, Burdwan - II Block)] |  |  | ORD/000653/2023-2024 | 4076/BWD | 13/09/2023 | 03/10/2023 | SSPR VALVE MANUFACTURING PVT LTD. | 20.63 | 2.5 | 12.12 | 100
7 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | Interconnection between pump house and delivery line and Construction of boundary wall at 2nd TW site for KHUDKURI PWSS under Khandaghosh Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000869/2023-2024 | 5309/BWD | 01/12/2023 | 30/01/2024 | JYOTI ENTERPRISE | 12.63 | 6.3 | 49.88 | 100
8 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Khundkuri Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000052/2023-2024 | 2513/CMD | 02/06/2023 | 02/07/2023 | RAJIB COMPANY | 28.95 | 11.93 | 41.22 | 98
9 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | KHUNDKURI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000753/2022-2023 | 1217/BWD | 16/03/2023 | 15/03/2024 | M/S JAN MAHAMMAD | 510.97 | 300.35 | 58.78 | 85
10 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | Continuation order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte for the period of 01.12.2023 to 31.05.2024 | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001007/2023-2024 | 2751/BSD | 28/11/2023 | 29/05/2024 | SK.ASFIA | 2.4 | 0.4 | 16.65 | 70
11 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 31/10/2024 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
Total | [13 empty] | 681.92 | 321.48 | 47.14