## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | Supply & delivery of different dia. MJ Coller for FHTC as well as smooth running of different W/S. Schemes under Burdwan Division, P.H.E. Dte. [i.e. (1) Magra PWSS, Memari-I Block, (2) Kuchut PWSS, Memari - II Block, (3) Khundkuri PWSS, Khandaghosh Block & (4) Samanti PWSS, Burdwan - II Block)] |  |  | ORD/000653/2023-2024 | 4076/BWD | 13/09/2023 | 03/10/2023 | SSPR VALVE MANUFACTURING PVT LTD. | 20.63 | 5 | 24.24 | 100
2 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | Material Requisition To Resource Division |  |  | RTOR000074/2022-2023 | 1253/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 16.58 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | Material Requisition To Resource Division |  |  | RTOR000106/2022-2023 | 1631/BWD | 06/04/2023 | 06/04/2023 | Resource Division | 12.19 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | Material Requisition To Resource Division |  |  | RTOR000705/2023-2024 | 5046/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | New service connection charges for Khundkuri PWSS TW-1 |  |  | BILL/01035/2023-2024 | BP-2023-24-115 | 16/08/2023 | 16/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.93 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | New service connection charges for Khundkuri PWSS TW-2 |  |  | BILL/01036/2023-2024 | BP-2023-24-116 | 16/08/2023 | 16/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.65 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | Continuation order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte for the period of 01.12.2023 to 31.05.2024 | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001007/2023-2024 | 2751/BSD | 28/11/2023 | 29/05/2024 | SK.ASFIA | 2.4 | 0.4 | 16.65 | 70
8 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 31/10/2024 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Khundkuri Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000052/2023-2024 | 2513/CMD | 02/06/2023 | 02/07/2023 | RAJIB COMPANY | 28.95 | 23.86 | 82.43 | 98
10 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | Interconnection between pump house and delivery line and Construction of boundary wall at 2nd TW site for KHUDKURI PWSS under Khandaghosh Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000869/2023-2024 | 5309/BWD | 01/12/2023 | 30/01/2024 | JYOTI ENTERPRISE | 12.63 | 12.6 | 99.76 | 100
11 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | KHUNDKURI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000753/2022-2023 | 1217/BWD | 16/03/2023 | 01/04/2025 | M/S JAN MAHAMMAD | 510.97 | 401.24 | 78.52 | 100
12 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | Supply of flow control devices for KHUNDKURI PWSS (SM/13465) under Burdwan Division, PHE Dte. | AE(HQs) | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000840/2024-2025 | 986/AE/HQ | 26/11/2024 | 04/02/2025 | MAKALI ENGINEERING CORPORATION | 8.33 | 0 | 0 | 100
13 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | Repairing damaged concrete road by Cement concrete (mix 1:1.5:3) and drainage system, Sluice valve chamber for FHTC work for KHANDAGHOSH, TARAPOSH, SAGRAI, SANKARI, KHUDKURI, ONARI PWSS and its adjoining mouzas within KHANDAGHOSH BLOCK under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000689/2024-2025 | 3684/BWD | 23/10/2024 | 01/04/2026 | SUPRIYA RAY | 115.68 | 0 | 0 | 20
14 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME | SM/13465 | New | Field level data validation of FHTC executed by Agencies on the basis of pictorial data with the objective of controlling multiple entry,improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database of KHUNDKURI Pipe Water Supply Scheme in Khandaghosh Block within Burdwan Sub-Division under Burdwan Division,PHE Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000890/2024-2025 | 2671/BSD | 04/12/2024 | 29/12/2025 | TECHVISION | 1.08 | 0 | 0 | 100
Total | [13 empty] | 807.01 | 443.1 | 54.91