## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari-I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/08/2023 to 31/10/2023] |  |  | ORD/000845/2023-2024 | 1759/BSD | 28/07/2023 | 02/10/2023 | MD HASIN | 0.85 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Memari-I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Supply & delivery of different dia. MJ Coller for FHTC as well as smooth running of different W/S. Schemes under Burdwan Division, P.H.E. Dte. [i.e. (1) Magra PWSS, Memari-I Block, (2) Kuchut PWSS, Memari - II Block, (3) Khundkuri PWSS, Khandaghosh Block & (4) Samanti PWSS, Burdwan - II Block)] |  |  | ORD/000653/2023-2024 | 4076/BWD | 13/09/2023 | 03/10/2023 | SSPR VALVE MANUFACTURING PVT LTD. | 20.63 | 0 | 0 | 100
3 | PURBA BARDHAMAN | Memari-I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Material Requisition To Resource Division |  |  | RTOR000070/2022-2023 | 1251/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 12.34 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari-I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Material Requisition To Resource Division |  |  | RTOR000462/2023-2024 | 3986/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 8.96 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Memari-I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Material Requisition To Resource Division |  |  | RTOR000676/2023-2024 | 5080/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Memari-I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.06.2024 to 31.07.2024] | AE(HQs) | J.E. 1 BURDWAN | ORD/000441/2024-2025 | 307/AE/HQ | 31/05/2024 | 31/07/2024 | MD HASIN | 0.8 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Memari-I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.02.2024 to 31.03.2024] | AE(HQs) | J.E. 1 BURDWAN | ORD/001204/2023-2024 | 42/AE/HQ | 29/01/2024 | 29/03/2024 | MD HASIN | 0.8 | 0 | 0 | 50
8 | PURBA BARDHAMAN | Memari-I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.08.2024 to 30.09.2024] | AE(HQs) | Contractual Junior Engineer | ORD/000508/2024-2025 | 548/AE/HQ | 01/08/2024 | 01/10/2024 | MD HASIN | 0.8 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Memari-I | Central Mechanical | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 31/10/2024 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Memari-I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.04.2024 to 31.05.2024] | AE(HQs) | J.E. 1 BURDWAN | ORD/001230/2023-2024 | 233/AE/HQ | 28/03/2024 | 28/05/2024 | MD HASIN | 0.8 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Memari-I | Central Mechanical | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | New Service connection for Magra PWSS TW-2. |  |  | BILL/02338/2023-2024 | BP-2023-24-474 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.7 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Memari-I | Central Mechanical | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | New service connection for Magra W/S Sechem. |  |  | BILL/02184/2023-2024 | BP-2023-24-379 | 16/01/2024 | 16/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.1 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Memari-I | Central Mechanical | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Magra Water Supply Scheme [ Block- Memari-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000650/2023-2024 | 3993/CMD | 29/08/2023 | 01/05/2025 | ORIENTAL ENGINEERING CO. | 29.35 | 0 | 0 | 100
14 | PURBA BARDHAMAN | Memari-I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.02.2025 to 31.03.2025] | AE(HQs) | Contractual Junior Engineer | ORD/001153/2024-2025 | 185/AE/HQ | 31/01/2025 | 31/03/2025 | MD HASIN | 0.8 | 0 | 0 | 0
15 | PURBA BARDHAMAN | Memari-I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.12.2024 to 31.01.2025] | AE(HQs) | Contractual Junior Engineer | ORD/000895/2024-2025 | 1009/AE/HQ | 29/11/2024 | 29/01/2025 | MD HASIN | 0.8 | 0 | 0 | 0
16 | PURBA BARDHAMAN | Memari-I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Field level data validation of FHTC executed by Agencies on the basis of pictorial data with the objective of controlling multiple entry,improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database of MAGRA Pipe Water Supply Scheme in Memari-I Block within Burdwan Sub-Division under Burdwan Division,PHE Dte |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000942/2024-2025 | 2731/BSD | 10/12/2024 | 29/12/2025 | TECHVISION | 0.8 | 0 | 0 | 100
17 | PURBA BARDHAMAN | Memari-I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.10.2024 to 30.11.2024] | AE(HQs) | Contractual Junior Engineer | ORD/000708/2024-2025 | 803/AE/HQ | 30/09/2024 | 30/11/2024 | MD HASIN | 0.8 | 0 | 0 | 0
18 | PURBA BARDHAMAN | Memari-I | Central Mechanical | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Supply and installation of Electro-Magnetic flow meter at HARIGRAM, KUCHUT & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000564/2024-2025 | 3103/CMD | 11/12/2024 | 09/02/2025 | S DUTTA | 15.06 | 0 | 0 | 0
19 | PURBA BARDHAMAN | Memari-I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.06.2025 to 31.07.2025] | AE(HQs), Burdwan Division, PHE Dte. | Contractual Junior Engineer | ORD/000167/2025-2026 | 689/AE/HQ | 30/05/2025 | 30/07/2025 | MD HASIN | 0.8 | 0 | 0 | 0
20 | PURBA BARDHAMAN | Memari-I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.04.2025 to 31.05.2025] | AE(HQs) | Contractual Junior Engineer | ORD/001404/2024-2025 | 455/AE/HQ | 28/03/2025 | 28/05/2025 | MD HASIN | 0.8 | 0 | 0 | 0
21 | PURBA BARDHAMAN | Memari-I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Restoration of Conc. road, Providing leftout FHTC with extension of Pipeline, construction of Pathway, drain, repairing of Pump House at Head Work site with allied works for MAGRA, SANUI, SATGACHIA Zone-I & NARAGOHALIA PIPED WATER SUPPLY SCHEME, Block-Memari-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001192/2024-2025 | 611/BWD | 11/02/2025 | 10/08/2025 | M/S ASHA CONSTRUCTION | 354.13 | 0 | 0 | 25
22 | PURBA BARDHAMAN | Memari-I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.10.2025 to 30.11.2025] |  | Contractual Junior Engineer | ORD/000700/2025-2026 | 1194/AE/HQ | 24/09/2025 | 24/11/2025 | MD HASIN | 0.8 | 0 | 0 | 0
23 | PURBA BARDHAMAN | Memari-I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.08.2025 to 30.09.2025] | AE(HQs), Burdwan Division, PHE Dte. | Contractual Junior Engineer | ORD/000527/2025-2026 | 1034/AE/HQ | 01/08/2025 | 01/10/2025 | MD HASIN | 0.8 | 0 | 0 | 0
24 | PURBA BARDHAMAN | Memari-I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.12.2025 to 31.01.2026] |  | Contractual Junior Engineer | ORD/000800/2025-2026 | 1280/AE/HQ | 01/12/2025 | 01/02/2026 | MD HASIN | 0.8 | 0 | 0 | 0
Total | [13 empty] | 533.6 | 0 | 0