## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Manteswar | Burdwan Division | SIGHNALI PIPED WATER SUPPLY SCHEME. | SM/13496 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to PASCHIM KHARAMPUR, SHUSHNA & SIGHNALI Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000482/2023-2024 | 3494/BWD | 09/08/2023 | 30/09/2025 | S.P. CONSTRUCTION | 1925.07 | 362.27 | 18.82 | 80
2 | PURBA BARDHAMAN | Manteswar | Central Mechanical | SIGHNALI PIPED WATER SUPPLY SCHEME. | SM/13496 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sighnali Water Supply Scheme [ Block- Monteshwar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000743/2023-2024 | 4053/CMD | 29/08/2023 | 01/05/2025 | ASHIM UDYOG | 27.76 | 0 | 0 | 100
3 | PURBA BARDHAMAN | Manteswar | Burdwan Division | SIGHNALI PIPED WATER SUPPLY SCHEME. | SM/13496 | New | Material Requisition To Resource Division |  |  | RTOR000453/2023-2024 | 3977/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 38.31 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Manteswar | Burdwan Division | SIGHNALI PIPED WATER SUPPLY SCHEME. | SM/13496 | New | Material Requisition To Resource Division |  |  | RTOR000321/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 15.55 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Manteswar | Central Mechanical | SIGHNALI PIPED WATER SUPPLY SCHEME. | SM/13496 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 31/10/2025 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
6 | PURBA BARDHAMAN | Manteswar | Central Mechanical | SIGHNALI PIPED WATER SUPPLY SCHEME. | SM/13496 | New | NEW SERVICE CONNECTION FOR SIGHNALI PWSS. |  |  | BILL/02692/2023-2024 | BP-2023-24-571 | 27/02/2024 | 27/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.01 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Manteswar | Central Mechanical | SIGHNALI PIPED WATER SUPPLY SCHEME. | SM/13496 | New | New service connection for SIGHNALI PWSS TW 1. |  |  | BILL/02445/2023-2024 | BP-2023-24-519 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.24 | 0 | 0 | 0
Total | [13 empty] | 2097 | 362.27 | 17.28