## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | KACHUA PIPED WATER SUPPLY SCHEME | SM/13497 | New | Material Requisition To Resource Division |  |  | RTOR000298/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 1.9 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | KACHUA PIPED WATER SUPPLY SCHEME | SM/13497 | New | Material Requisition To Resource Division |  |  | RTOR000473/2023-2024 | 3997/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 0.55 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | KACHUA PIPED WATER SUPPLY SCHEME | SM/13497 | New | Material Requisition To Resource Division |  |  | RTOR000799/2023-2024 | 310/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 17.19 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | KACHUA PIPED WATER SUPPLY SCHEME | SM/13497 | New | New service connection for KACHUA PWSS TW-2. |  |  | BILL/02396/2023-2024 | BP-2023-24-505 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.03 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | KACHUA PIPED WATER SUPPLY SCHEME | SM/13497 | New | New service connection for KACHUA PWSS TW-1. |  |  | BILL/02395/2023-2024 | BP-2023-24-504 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.27 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | KACHUA PIPED WATER SUPPLY SCHEME | SM/13497 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KACHUA & KAMALPUR Piped Water Supply Scheme under Purbasthali ¿ I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000133/2023-2024 | 2344/BWD | 22/05/2023 | 01/10/2025 | CONCORD ENGINEERING | 470.92 | 169.93 | 36.08 | 40
7 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | KACHUA PIPED WATER SUPPLY SCHEME | SM/13497 | New | Different Types of work involved in connection with Augmentation of SONARUDRA (SM/16349) & KACHUA (SM/13497) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000192/2024-2025 | 2430/BWD | 27/06/2024 | 20/10/2025 | R.G. INFRASTRUCTURE | 240.7 | 103.84 | 43.14 | 2
8 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | KACHUA PIPED WATER SUPPLY SCHEME | SM/13497 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000072/2024-2025 | 2397/CMD | 02/08/2024 | 31/10/2024 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 0 | 30
Total | [13 empty] | 788.16 | 273.76 | 34.73