## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | UKHRID PIPED WATER SUPPLY SCHEME | SM/13505 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMRA, BALABATI, UKHRID & RUPSA Piped Water Supply Scheme under KHANDAGHOSH Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte.,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000008/2023-2024 | 1726/BWD | 13/04/2023 | 01/10/2025 | S.P. CONSTRUCTION | 1710.27 | 276.07 | 16.14 | 45
2 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | UKHRID PIPED WATER SUPPLY SCHEME | SM/13505 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Ukhrid Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000708/2023-2024 | 4019/CMD | 29/08/2023 | 28/09/2023 | C.M. ENTERPRISE | 28.88 | 23.89 | 82.71 | 100
3 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | UKHRID PIPED WATER SUPPLY SCHEME | SM/13505 | New | Material Requisition To Resource Division |  |  | RTOR000082/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 31.25 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | UKHRID PIPED WATER SUPPLY SCHEME | SM/13505 | New | Material Requisition To Resource Division |  |  | RTOR000165/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 12.6 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | UKHRID PIPED WATER SUPPLY SCHEME | SM/13505 | New | Material Requisition To Resource Division |  |  | RTOR000736/2023-2024 | 5234/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 21.07 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | UKHRID PIPED WATER SUPPLY SCHEME | SM/13505 | New | Quotation for new service connection at Ukhrid W/S Scheme PH-II. |  |  | BILL/01810/2023-2024 | BP-2023-24-304 | 30/12/2023 | 30/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.29 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | UKHRID PIPED WATER SUPPLY SCHEME | SM/13505 | New | Quotation for new service connection at UKHRID W/S Scheme PH-I. |  |  | BILL/01816/2023-2024 | BP-2023-24-303 | 30/12/2023 | 30/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.54 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | UKHRID PIPED WATER SUPPLY SCHEME | SM/13505 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 31/10/2024 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
Total | [13 empty] | 1859.44 | 299.96 | 16.13