## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari-I | Burdwan Division | DEHA PIPED WATER SUPPLY SCHEME | SM/13506 | New | Material Requisition To Resource Division |  |  | RTOR000238/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 8.9 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Memari-I | Burdwan Division | DEHA PIPED WATER SUPPLY SCHEME | SM/13506 | New | Material Requisition To Resource Division |  |  | RTOR000463/2023-2024 | 3987/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 4.94 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Memari-I | Burdwan Division | DEHA PIPED WATER SUPPLY SCHEME | SM/13506 | New | Material Requisition To Resource Division |  |  | RTOR000664/2023-2024 | 5103/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari-I | Burdwan Division | DEHA PIPED WATER SUPPLY SCHEME | SM/13506 | New | Continuation order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte for the period of 01.12.2023 to 31.05.2024 | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001007/2023-2024 | 2751/BSD | 28/11/2023 | 29/05/2024 | SK.ASFIA | 2.4 | 0.4 | 16.65 | 70
5 | PURBA BARDHAMAN | Memari-I | Burdwan Division | DEHA PIPED WATER SUPPLY SCHEME | SM/13506 | New | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-09-2024 to 30-11-2024 | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000682/2024-2025 | 1957/BSD | 30/08/2024 | 29/11/2024 | SK. ASFIA | 1.2 | 0.4 | 33.29 | 60
6 | PURBA BARDHAMAN | Memari-I | Central Mechanical | DEHA PIPED WATER SUPPLY SCHEME | SM/13506 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at DEHA Water Supply Scheme [ Block- MEMARI-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000807/2023-2024 | 4092/CMD | 29/08/2023 | 01/01/2025 | ORIENTAL ENGINEERING CO. | 29.39 | 20.12 | 68.47 | 100
7 | PURBA BARDHAMAN | Memari-I | Central Mechanical | DEHA PIPED WATER SUPPLY SCHEME | SM/13506 | New | Quotation for new electric service connection at Deha PH NO.-2 |  |  | BILL/01737/2023-2024 | BP-2023-24-241 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.48 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Memari-I | Central Mechanical | DEHA PIPED WATER SUPPLY SCHEME | SM/13506 | New | Quotation for new electric service connection at Deha PH NO.-1 |  |  | BILL/01738/2023-2024 | BP-2023-24-242 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.27 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Memari-I | Burdwan Division | DEHA PIPED WATER SUPPLY SCHEME | SM/13506 | New | Restoration of concrete road by Cement concrete (mix 1:1.5:3),Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for DURGADANGA SVS & DEHA PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001039/2024-2025 | 141/BWD | 08/01/2025 | 08/04/2025 | MUKHERJEE ENTERPRISE | 64.37 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Memari-I | Burdwan Division | DEHA PIPED WATER SUPPLY SCHEME | SM/13506 | New | Continuation Work Order for Supply of one No.Diesel Driven Ambassador Car No. WB:41H-4009 on hire basis for the office of the Assistant Engineer,Burdwan Sub-Division,PHE Dte(Period from 01-03-2025 to 31.05.2025) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001407/2024-2025 | 457/BSD | 28/02/2025 | 29/05/2025 | SK. ASFIA | 1.2 | 0.4 | 33.27 | 100
11 | PURBA BARDHAMAN | Memari-I | Burdwan Division | DEHA PIPED WATER SUPPLY SCHEME | SM/13506 | New | Material Requisition To Resource Division |  |  | RTOR000065/2024-2025 | 391/BWD | 17/01/2025 | 17/01/2025 | Resource Division | 0.44 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Memari-I | Burdwan Division | DEHA PIPED WATER SUPPLY SCHEME | SM/13506 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEHA & BIJRA Piped Water Supply Scheme under Memari I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000092/2023-2024 | 2215/BWD | 15/05/2023 | 01/04/2026 | CONCORD ENGINEERING | 868.87 | 208.27 | 23.97 | 60
Total | [13 empty] | 1008.92 | 229.59 | 22.76