## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Bhatar | Burdwan Division | KHURUL PIPED WATER SUPPLY SCHEME | SM/13549 | New | Material Requisition To Resource Division |  |  | RTOR000386/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 6.52 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Bhatar | Burdwan Division | KHURUL PIPED WATER SUPPLY SCHEME | SM/13549 | New | Material Requisition To Resource Division |  |  | RTOR000606/2023-2024 | 4911/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 32.92 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Bhatar | Burdwan Division | KHURUL PIPED WATER SUPPLY SCHEME | SM/13549 | New | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 23.91 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Bhatar | Central Mechanical | KHURUL PIPED WATER SUPPLY SCHEME | SM/13549 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 31/10/2024 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Bhatar | Central Mechanical | KHURUL PIPED WATER SUPPLY SCHEME | SM/13549 | New | NEW SERVICE CONNECTION FOR KHURUL PIPED WATER SUPPLY SCHEME. |  |  | BILL/02832/2023-2024 | BP-2023-24-589 | 04/03/2024 | 04/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.45 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Bhatar | Central Mechanical | KHURUL PIPED WATER SUPPLY SCHEME | SM/13549 | New | NEW SERVICE CONNECTION FOR KHURUL PIPED WATER SUPPLY SCHEME. |  |  | BILL/02831/2023-2024 | BP-2023-24-588 | 04/03/2024 | 04/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.72 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Bhatar | Central Mechanical | KHURUL PIPED WATER SUPPLY SCHEME | SM/13549 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KHURUL Water Supply Scheme [ Block- BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000803/2023-2024 | 4089/CMD | 29/08/2023 | 28/09/2023 | M/S, S.S. ENTERPRISE. | 27.79 | 0 | 0 | 60
Total | [13 empty] | 180.31 | 0 | 0