## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Bhatar | Burdwan Division | BALSIDANGA PIPED WATER SUPPLY SCHEME | SM/13904 | New | BALSIDANGA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under BHATAR Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000793/2022-2023 | 1443/BWD | 24/03/2023 | 22/06/2023 | G.S. CONSTRUCTION & CO. | 60.82 | 29.27 | 48.12 | 100
2 | PURBA BARDHAMAN | Bhatar | Central Mechanical | BALSIDANGA PIPED WATER SUPPLY SCHEME | SM/13904 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Balsidanga Water Supply Scheme [ Block- Bhatar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000137/2023-2024 | 2818/CMD | 04/07/2023 | 04/04/2025 | M/S. SWAPAN BANERJEE | 26.97 | 11.6 | 43.01 | 60
3 | PURBA BARDHAMAN | Bhatar | Burdwan Division | BALSIDANGA PIPED WATER SUPPLY SCHEME | SM/13904 | New | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 14.19 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Bhatar | Burdwan Division | BALSIDANGA PIPED WATER SUPPLY SCHEME | SM/13904 | New | Material Requisition To Resource Division |  |  | RTOR000158/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 9.5 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Bhatar | Burdwan Division | BALSIDANGA PIPED WATER SUPPLY SCHEME | SM/13904 | New | Material Requisition To Resource Division |  |  | RTOR000754/2023-2024 | 5256/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 18.5 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Bhatar | Central Mechanical | BALSIDANGA PIPED WATER SUPPLY SCHEME | SM/13904 | New | New service connection charges for Balsidanga PWSS TW-1 |  |  | BILL/00774/2023-2024 | BP-2023-24-71 | 21/07/2023 | 21/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.28 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Bhatar | Central Mechanical | BALSIDANGA PIPED WATER SUPPLY SCHEME | SM/13904 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 31/10/2024 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Bhatar | Burdwan Division | BALSIDANGA PIPED WATER SUPPLY SCHEME | SM/13904 | New | Sinking of 250 X 150 mm dia Tubewell, Construction of pump House, Connection with pump house and Modification to distribution network by making a loop and extension with uPVC pipe to augment the water supply to FHTC at Beldanga and Kanchgoria village of BALSHIDANGA W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE | ORD/001220/2023-2024 | 1017/BWD | 07/03/2024 | 06/05/2024 | BAMDEB CONSTRUCTION & CO | 40.65 | 40.65 | 99.99 | 100
9 | PURBA BARDHAMAN | Bhatar | Burdwan Division | BALSIDANGA PIPED WATER SUPPLY SCHEME | SM/13904 | New | Additional work for BALSIDANGA Piped Water Supply Scheme with FHTC & approach road with bullah pilling under Bhatar Block, District:- Purba Bardhaman [New SCHEME]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000573/2024-2025 | 3314/BWD | 06/09/2024 | 05/12/2024 | KALYAN CHOWDHURY | 14.81 | 0 | 0 | 100
10 | PURBA BARDHAMAN | Bhatar | Central Mechanical | BALSIDANGA PIPED WATER SUPPLY SCHEME | SM/13904 | New | ADDITIONAL QUOTATION NEW SERVICE CONNECTION FOR BALSIDNAGA PWSS TW -1. |  |  | BILL/03105/2023-2024 | BP-2023-24-645 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.04 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Bhatar | Central Mechanical | BALSIDANGA PIPED WATER SUPPLY SCHEME | SM/13904 | New | Quotation for new service connection at Balsidanga PWSS PH-2. |  |  | BILL/00388/2024-2025 | BP-2024-25-203 | 18/07/2024 | 18/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.09 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Bhatar | Burdwan Division | BALSIDANGA PIPED WATER SUPPLY SCHEME | SM/13904 | New | Land Development work , Remaining FHTC at Balsidanga Piped Water Supply Scheme , P.H.E Dte. Block:-Bhatar Dist: Purba Bardhaman. |  | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000315/2025-2026 | 1064/DSD | 24/07/2025 | 17/11/2025 | KALYAN CHOWDHURY | 1.93 | 0 | 0 | 100
13 | PURBA BARDHAMAN | Bhatar | Burdwan Division | BALSIDANGA PIPED WATER SUPPLY SCHEME | SM/13904 | New | Extension of HDPE Pipe Line at Kanchgoria and Beldanga village Under Balshidanga W/S Schweme WITHIN Durgapur (Burdwan North) Sub Division, Under Burdwan Division PHE Dte. |  | JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE | ORD/000312/2025-2026 | 1062/DSD | 24/07/2025 | 23/08/2025 | BAMDEB CONSTRUCTION & CO | 4.87 | 0 | 0 | 100
Total | [13 empty] | 288.66 | 81.52 | 28.24