## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | GOPALBERA PIPED WATER SUPPLY SCHEME | SM/13905 | New | Material Requisition To Resource Division |  |  | RTOR000105/2023-2024 | 1965/BWD | 26/04/2023 | 26/04/2023 | Resource Division | 9.42 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | GOPALBERA PIPED WATER SUPPLY SCHEME | SM/13905 | New | Material Requisition To Resource Division |  |  | RTOR000715/2023-2024 | 5269/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 21.07 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | GOPALBERA PIPED WATER SUPPLY SCHEME | SM/13905 | New | Material Requisition To Resource Division |  |  | RTOR000192/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 11.22 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | GOPALBERA PIPED WATER SUPPLY SCHEME | SM/13905 | New | New service connection for Gopalbera PWSS TW -1. |  |  | BILL/02415/2023-2024 | BP-2023-24-513 | 08/02/2024 | 08/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.42 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | GOPALBERA PIPED WATER SUPPLY SCHEME | SM/13905 | New | New service connection for Gopalbera PWSS TW -2. |  |  | BILL/02416/2023-2024 | BP-2023-24-514 | 08/02/2024 | 08/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.28 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | GOPALBERA PIPED WATER SUPPLY SCHEME | SM/13905 | New | GOPALBERA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte.,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000081/2023-2024 | 2079/BWD | 04/05/2023 | 01/04/2025 | KHAN ENTERPRISE | 588.35 | 436.82 | 74.24 | 50
7 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | GOPALBERA PIPED WATER SUPPLY SCHEME | SM/13905 | New | Balance work for providing Functional Household Tap Connection (FHTC) within command area GOPALBERA & CHAGRAM W/S. Scheme of Khandaghosh Block under Burdwan Divn., PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000959/2024-2025 | 4438/BWD | 18/12/2024 | 28/08/2025 | DUBE ENTERPRISE | 143.33 | 0 | 0 | 70
8 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | GOPALBERA PIPED WATER SUPPLY SCHEME | SM/13905 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000071/2024-2025 | 2391/CMD | 02/08/2024 | 31/10/2024 | C.M. ENTERPRISE | 45.81 | 0 | 0 | 10
9 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | GOPALBERA PIPED WATER SUPPLY SCHEME | SM/13905 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Gopalbera Water Supply Scheme [ Block- Khandoghosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000732/2023-2024 | 4042/CMD | 29/08/2023 | 28/09/2023 | ASHIM UDYOG | 28.95 | 22.76 | 78.64 | 100
Total | [13 empty] | 858.84 | 459.58 | 53.51