## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari-I | Burdwan Division | CHOTKHANDA PIPED WATER SUPPLY SCHEME | SM/13907 | New | CHOTKHANDA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000123/2023-2024 | 2306/BWD | 19/05/2023 | 01/04/2025 | ASHOK KUMAR GHOSH | 513.64 | 371.17 | 72.26 | 90
2 | PURBA BARDHAMAN | Memari-I | Central Mechanical | CHOTKHANDA PIPED WATER SUPPLY SCHEME | SM/13907 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chotkhanda Water Supply Scheme [ Block- Memari-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000731/2023-2024 | 4041/CMD | 29/08/2023 | 01/09/2024 | S.K. ENTERPRISE | 29.59 | 23.57 | 79.64 | 100
3 | PURBA BARDHAMAN | Memari-I | Burdwan Division | CHOTKHANDA PIPED WATER SUPPLY SCHEME | SM/13907 | New | Material Requisition To Resource Division |  |  | RTOR000236/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 7.93 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari-I | Burdwan Division | CHOTKHANDA PIPED WATER SUPPLY SCHEME | SM/13907 | New | Material Requisition To Resource Division |  |  | RTOR000467/2023-2024 | 3991/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 9.08 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Memari-I | Burdwan Division | CHOTKHANDA PIPED WATER SUPPLY SCHEME | SM/13907 | New | Material Requisition To Resource Division |  |  | RTOR000663/2023-2024 | 5085/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Memari-I | Central Mechanical | CHOTKHANDA PIPED WATER SUPPLY SCHEME | SM/13907 | New | New service connection charges for Chotkhanda PWSS TW-1 |  |  | BILL/01728/2023-2024 | BP-2023-24-244 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.02 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Memari-I | Central Mechanical | CHOTKHANDA PIPED WATER SUPPLY SCHEME | SM/13907 | New | Quotation for new electric service connection at Chotkhanda TW NO.-2 |  |  | BILL/01740/2023-2024 | BP-2023-24-243 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.61 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Memari-I | Burdwan Division | CHOTKHANDA PIPED WATER SUPPLY SCHEME | SM/13907 | New | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, land development, Sluice valve chamber for smooth water supply of FHTC work for CHOTKHANDA PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000930/2024-2025 | 4280/BWD | 09/12/2024 | 09/03/2025 | TARAMA AGENCY | 21.09 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Memari-I | Central Mechanical | CHOTKHANDA PIPED WATER SUPPLY SCHEME | SM/13907 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 31/10/2024 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Memari-I | Central Mechanical | CHOTKHANDA PIPED WATER SUPPLY SCHEME | SM/13907 | New | Supply & delivery of different electro-mechanical accessories (for urgent FHTC) for Tube well no.-I & II at Chotkhanda w/s scheme, (Block- Memari-1) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/001902/2023-2024 | 540/CMSD | 28/03/2024 | 04/04/2024 | S.K. ENTERPRISE | 0.53 | 0.53 | 100 | 100
11 | PURBA BARDHAMAN | Memari-I | Burdwan Division | CHOTKHANDA PIPED WATER SUPPLY SCHEME | SM/13907 | New | Material Requisition To Resource Division |  |  | RTOR000061/2024-2025 | 387/BWD | 17/01/2025 | 17/01/2025 | Resource Division | 9.6 | 0 | 0 | 0
Total | [13 empty] | 673.18 | 395.27 | 58.72