## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | CHAGRAM PIPED WATER SUPPLY SCHEME | SM/13941 | New | Material Requisition To Resource Division |  |  | RTOR000104/2023-2024 | 1965/BWD | 26/04/2023 | 26/04/2023 | Resource Division | 18.8 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | CHAGRAM PIPED WATER SUPPLY SCHEME | SM/13941 | New | Material Requisition To Resource Division |  |  | RTOR000190/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 10.42 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | CHAGRAM PIPED WATER SUPPLY SCHEME | SM/13941 | New | Material Requisition To Resource Division |  |  | RTOR000712/2023-2024 | 5043/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | CHAGRAM PIPED WATER SUPPLY SCHEME | SM/13941 | New | New service connection charges for Chagram PWSS TW-1 |  |  | BILL/00819/2023-2024 | BP-2023-24-95 | 02/08/2023 | 02/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.24 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | CHAGRAM PIPED WATER SUPPLY SCHEME | SM/13941 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chagram Water Supply Scheme [ Block- Khandoghosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000213/2023-2024 | 3068/CMD | 21/07/2023 | 20/08/2023 | PADMA ENGINEERING CO. | 28.96 | 23.67 | 81.74 | 100
6 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | CHAGRAM PIPED WATER SUPPLY SCHEME | SM/13941 | New | New Electric connection Chagram W/S PH-II |  |  | BILL/01791/2023-2024 | BP-2023-24-306 | 30/12/2023 | 30/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.27 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | CHAGRAM PIPED WATER SUPPLY SCHEME | SM/13941 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHAGRAM & KHEJURHATI Piped Water Supply Scheme under Khandaghosh Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte.,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000083/2023-2024 | 2080/BWD | 04/05/2023 | 01/04/2025 | KHAN ENTERPRISE | 688.15 | 332.98 | 48.39 | 58
8 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | CHAGRAM PIPED WATER SUPPLY SCHEME | SM/13941 | New | Balance work for providing Functional Household Tap Connection (FHTC) within command area GOPALBERA & CHAGRAM W/S. Scheme of Khandaghosh Block under Burdwan Divn., PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000959/2024-2025 | 4438/BWD | 18/12/2024 | 28/08/2025 | DUBE ENTERPRISE | 143.33 | 0 | 0 | 70
9 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | CHAGRAM PIPED WATER SUPPLY SCHEME | SM/13941 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000071/2024-2025 | 2391/CMD | 02/08/2024 | 31/10/2024 | C.M. ENTERPRISE | 45.81 | 0 | 0 | 10
10 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | CHAGRAM PIPED WATER SUPPLY SCHEME | SM/13941 | New | Continuation for Operation of Distribution System, Rising main, Sluice Valves, including operation of sluice valves of CHAGRAM PWSS within Durgapur Sub-Division under Burdwan Division, PHE Dte. [Period for 01/04/2026 TO 30/06/2026]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001125/2025-2026 | 227/DSD | 27/03/2026 | 26/06/2026 | ANWESHA CONSTRUCTION | 0.63 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | CHAGRAM PIPED WATER SUPPLY SCHEME | SM/13941 | New | Continuation for Operation of Distribution System, Rising main, Sluice Valves, including operation of sluice valves of CHAGRAM PWSS within Durgapur Sub-Division under Burdwan Division, PHE Dte. [Period for 01.10.2025 to 31.12.2025]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000780/2025-2026 | 1255/DSD | 24/09/2025 | 02/01/2026 | ANWESHA CONSTRUCTION | 0.63 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | CHAGRAM PIPED WATER SUPPLY SCHEME | SM/13941 | New | Continuation for Operation of Distribution System, Rising main, Sluice Valves, including operation of sluice valves of CHAGRAM PWSS within Durgapur Sub-Division under Burdwan Division, PHE Dte. [Period for 01/01/2026 TO 31/03/2026]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001107/2025-2026 | 1465/DSD | 30/12/2025 | 30/03/2026 | ANWESHA CONSTRUCTION | 0.63 | 0 | 0 | 0
Total | [13 empty] | 964.31 | 356.64 | 36.98