## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KAMALPUR PIPED WATER SUPPLY SCHEME | SM/13942 | New | Material Requisition To Resource Division |  |  | RTOR000106/2023-2024 | 1965/BWD | 26/04/2023 | 26/04/2023 | Resource Division | 5.64 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KAMALPUR PIPED WATER SUPPLY SCHEME | SM/13942 | New | Material Requisition To Resource Division |  |  | RTOR000193/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 14.43 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KAMALPUR PIPED WATER SUPPLY SCHEME | SM/13942 | New | Material Requisition To Resource Division |  |  | RTOR000306/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 19.29 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KAMALPUR PIPED WATER SUPPLY SCHEME | SM/13942 | New | Material Requisition To Resource Division |  |  | RTOR000720/2023-2024 | 5266/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 21.07 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KAMALPUR PIPED WATER SUPPLY SCHEME | SM/13942 | New | Continuation order for Supply of 01(one) No. Diesel Driven Motor Cab (Bharat Stage-II) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Division (Burdwan North) P.H.E. Dte. Govt. of West Bengal (for the period of 01/01/2024 to 31/05/2024) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001180/2023-2024 | 995/DSD | 29/12/2023 | 29/06/2024 | SUJAUDDIN SEKH | 2 | 0 | 0 | 60
6 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | KAMALPUR PIPED WATER SUPPLY SCHEME | SM/13942 | New | NEW SERVICE CONNECTION FOR KAMALPUR PWSS PH-2. |  |  | BILL/02874/2023-2024 | BP-2023-24-602 | 06/03/2024 | 06/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.8 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | KAMALPUR PIPED WATER SUPPLY SCHEME | SM/13942 | New | NEW SERVICE CONNECTION FOR KAMALPUR PWSS PH-1. |  |  | BILL/02870/2023-2024 | BP-2023-24-601 | 06/03/2024 | 06/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.95 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | KAMALPUR PIPED WATER SUPPLY SCHEME | SM/13942 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SARANGA & KAMALPUR Piped Water Supply Scheme under Khandaghosh Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte.,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000082/2023-2024 | 2078/BWD | 04/05/2023 | 01/04/2025 | KHAN ENTERPRISE | 820.73 | 0 | 0 | 42
9 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | KAMALPUR PIPED WATER SUPPLY SCHEME | SM/13942 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000071/2024-2025 | 2391/CMD | 02/08/2024 | 31/10/2024 | C.M. ENTERPRISE | 45.81 | 0 | 0 | 10
10 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | KAMALPUR PIPED WATER SUPPLY SCHEME | SM/13942 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000714/2024-2025 | 2979/CMD | 25/11/2024 | 23/02/2025 | H.K. DAS & CO. | 53.27 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | KAMALPUR PIPED WATER SUPPLY SCHEME | SM/13942 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kamalpur Water Supply Scheme [ Block- Khandoghosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000733/2023-2024 | 4043/CMD | 29/08/2023 | 28/09/2023 | M/S. SWAPAN BANERJEE | 28.97 | 0 | 0 | 100
Total | [13 empty] | 1016.95 | 0 | 0