## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | KURMUN PIPED WATER SUPPLY SCHEME | SM/13943 | New | Material Requisition To Resource Division |  |  | RTOR000102/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 9.02 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | KURMUN PIPED WATER SUPPLY SCHEME | SM/13943 | New | Material Requisition To Resource Division |  |  | RTOR000391/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 9.67 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | KURMUN PIPED WATER SUPPLY SCHEME | SM/13943 | New | Material Requisition To Resource Division |  |  | RTOR000725/2023-2024 | 5271/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 21.07 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | KURMUN PIPED WATER SUPPLY SCHEME | SM/13943 | New | New service connection charges for Kurmun PWSS TW-1 |  |  | BILL/01675/2023-2024 | BP-2023-24-226 | 10/11/2023 | 10/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | KURMUN PIPED WATER SUPPLY SCHEME | SM/13943 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 31/10/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | KURMUN PIPED WATER SUPPLY SCHEME | SM/13943 | New | Supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-02-2024 to 30-04-2024) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001181/2023-2024 | 188/BSD | 31/01/2024 | 06/04/2024 | PARVIN BEGAM | 0.85 | 0.28 | 33.21 | 97
7 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | KURMUN PIPED WATER SUPPLY SCHEME | SM/13943 | New | Supply, delivery, installation & hand hold demonstration of different equipments / machineries to test HDPE pipes as per IS: 4984-2016 at the pipe testing laboratory at Nababhat under Burdwan Division, PHE. Dte._2ND CALL | AE(HQs) | J.E. 1 BURDWAN | ORD/001212/2023-2024 | 907/BWD | 04/03/2024 | 03/04/2024 | MANASH GHOSH | 23.87 | 4.93 | 20.67 | 100
8 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | KURMUN PIPED WATER SUPPLY SCHEME | SM/13943 | New | New service connection for Kurmun PWSS |  |  | BILL/02857/2023-2024 | BP-2023-24-603 | 06/03/2024 | 06/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.63 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | KURMUN PIPED WATER SUPPLY SCHEME | SM/13943 | New | KURMUN Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000659/2023-2024 | 4124/BWD | 14/09/2023 | 10/12/2025 | GHOSH CONCERN | 550.63 | 131.72 | 23.92 | 65
10 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | KURMUN PIPED WATER SUPPLY SCHEME | SM/13943 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kurmun Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000658/2023-2024 | 4001/CMD | 29/08/2023 | 28/09/2023 | S.P. CONSTRUCTION | 28.96 | 22.95 | 79.25 | 100
11 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | KURMUN PIPED WATER SUPPLY SCHEME | SM/13943 | New | Balance work [ i.e. Extension or parallel Pipeline, Leftout FHTC, Road Restoration work, Sinking of Additional Tube Well with Pump House & Boundary wall, inter Connection of Additional Tube Well, with allied work of KURMUN Piped Water Supply Scheme, Block-Burdwan- I under Burdwan Sub Division, PHE Dte. within Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001220/2024-2025 | 727/BWD | 24/02/2025 | 24/06/2025 | SHIVAM UN-EMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 95.65 | 0 | 0 | 0
Total | [13 empty] | 804.28 | 159.88 | 19.88