## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | BAKALSA PIPED WATER SUPPLY SCHEME | SM/13944 | New | Material Requisition To Resource Division |  |  | RTOR000090/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 3.25 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | BAKALSA PIPED WATER SUPPLY SCHEME | SM/13944 | New | Material Requisition To Resource Division |  |  | RTOR000222/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 21.15 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | BAKALSA PIPED WATER SUPPLY SCHEME | SM/13944 | New | Material Requisition To Resource Division |  |  | RTOR000708/2023-2024 | 5041/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | BAKALSA PIPED WATER SUPPLY SCHEME | SM/13944 | New | Material Requisition To Resource Division |  |  | RTOR000575/2023-2024 | 4893/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 6.5 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | BAKALSA PIPED WATER SUPPLY SCHEME | SM/13944 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 31/10/2024 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | BAKALSA PIPED WATER SUPPLY SCHEME | SM/13944 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 31/10/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | BAKALSA PIPED WATER SUPPLY SCHEME | SM/13944 | New | Supply, delivery, installation & hand hold demonstration of different equipments / machineries to test HDPE pipes as per IS: 4984-2016 at the pipe testing laboratory at Nababhat under Burdwan Division, PHE. Dte._2ND CALL | AE(HQs) | J.E. 1 BURDWAN | ORD/001212/2023-2024 | 907/BWD | 04/03/2024 | 03/04/2024 | MANASH GHOSH | 23.87 | 4.99 | 20.93 | 100
8 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | BAKALSA PIPED WATER SUPPLY SCHEME | SM/13944 | New | New service connection charges for Bakalsa PWSS TW-1 |  |  | BILL/01828/2023-2024 | BP-2023-24-336 | 06/01/2024 | 06/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.04 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | BAKALSA PIPED WATER SUPPLY SCHEME | SM/13944 | New | New service connection for Bakalsa PWSS. |  |  | BILL/02248/2023-2024 | BP-2023-24-395 | 17/01/2024 | 17/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.99 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | BAKALSA PIPED WATER SUPPLY SCHEME | SM/13944 | New | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation, construction of switch room, boundary walls with gates, land development, surface drains and internal pathways at different TW site for BAKALSA Piped Water Supply Scheme under BURDWAN-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JE (RWS) Burdwan-I Block | ORD/000573/2023-2024 | 3723/BWD | 25/08/2023 | 21/08/2025 | M/S GHOSH & CO. | 534.23 | 166.72 | 31.21 | 25
Total | [13 empty] | 755.71 | 171.72 | 22.72