## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | JAGADABAD PIPED WATER SUPPLY SCHEME | SM/13945 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Jagadbad Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000654/2023-2024 | 3997/CMD | 29/08/2023 | 28/09/2023 | CHOUDHURY ENTERPRISE | 28.93 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | JAGADABAD PIPED WATER SUPPLY SCHEME | SM/13945 | New | Material Requisition To Resource Division |  |  | RTOR000094/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 8.29 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | JAGADABAD PIPED WATER SUPPLY SCHEME | SM/13945 | New | Material Requisition To Resource Division |  |  | RTOR000286/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 17.21 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | JAGADABAD PIPED WATER SUPPLY SCHEME | SM/13945 | New | Material Requisition To Resource Division |  |  | RTOR000718/2023-2024 | 5274/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 21.07 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | JAGADABAD PIPED WATER SUPPLY SCHEME | SM/13945 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 31/10/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | JAGADABAD PIPED WATER SUPPLY SCHEME | SM/13945 | New | NEW SERVICE CONNECTION FOR JAGDABAD PWSS PH-1. |  |  | BILL/02872/2023-2024 | BP-2023-24-609 | 06/03/2024 | 06/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.65 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | JAGADABAD PIPED WATER SUPPLY SCHEME | SM/13945 | New | NEW SERVICE CONNECTION FOR JAGDABAD PWSS PH-2. |  |  | BILL/02873/2023-2024 | BP-2023-24-608 | 06/03/2024 | 06/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.21 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | JAGADABAD PIPED WATER SUPPLY SCHEME | SM/13945 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BARASAT, JAGADABAD & KHAIDYA Piped Water Supply Scheme under BURDWAN-I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | J.E. 1 BURDWAN | ORD/000465/2023-2024 | 3460/BWD | 08/08/2023 | 29/09/2025 | CONCORD EMC ENCLAVE LLP | 1526.24 | 229 | 15 | 5
9 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | JAGADABAD PIPED WATER SUPPLY SCHEME | SM/13945 | New | Continuation for the work of Supply of one No. Diesel Driven Car (other than Ambasader) on hire basis for the office of the Assistant Engineer, RWS Burdwan Sub- Division, PHE Dte. (Period from 01-11-2025 to 31-12-2025). | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE |  | ORD/000751/2025-2026 | 239/RWS | 31/10/2025 | 31/12/2025 | MD HASIN | 0.8 | 0 | 0 | 0
Total | [13 empty] | 1669.35 | 229 | 13.72